## Guide
ATS Weekly Data – User Guide
One workbook, filled once a week, feeds BOTH the Weekly Report and the Monthly Council dashboard.
SAMPLE DATA – fictional illustrative history for this portfolio; replace before presenting
Data Mode on the Config sheet = SAMPLE. The history in this file is made up so you can try the dashboard. Replace it with your own rows, then set Data Mode to LIVE.
1. The idea: fill once, weekly
• Every Friday you add ONE new row to Weekly_Snapshot and one row per active topic to Topic_Progress and Readiness; defects, TSRs and milestones are updated whenever they change. Nothing is ever overwritten: history is kept as dated rows.
• A WEEK is a slice (the latest Week Ending). A MONTH or QUARTER is a roll-up of the weeks in it (see section 4). That is how the same file feeds the Weekly Report and the Monthly Council.
• Yellow cells (blue text) are for you to type or pick from a dropdown. Grey cells are formulas – never type over them. Dates are real dates shown as yyyy-mm-dd; use Alt+Enter for a new line inside a text cell.
• Do not rename sheets, rename or reorder column headers, or insert columns: the dashboard finds columns by header text. Adding new rows below the last row is always safe (about 300 rows are pre-formatted on each data sheet).
2. What to update and when
When | Sheet | What to do | Rows
Weekly (every Friday) | Weekly_Snapshot | Add 1 new row for the new Week Ending (a Friday). Enter cumulative-to-date counts, test days, downtime hours, FTE, spend and the Overall RAG + summary. | 1 per week
Weekly | Topic_Progress | 1 row per active topic: phase, test cases planned / designed, and cumulative passed, failed, blocked. | 1 per topic per week
Weekly | Defect_Log | Add new defects; update Status, Resolved Date, TCs Blocked and Triage Comments on existing ones. | As needed
Weekly | Readiness | 1 row per topic: planned SIT start, overall RAG, six readiness areas (RAG + note) and Road to Green. | 1 per topic per week
Weekly (optional) | Commentary | Narrative per KPI for the week: highlights, concern, actions, executive commentary; optional RAG / current-position override. | 0–16 per week
As they happen | TSR_Log | Add a TSR when received; fill Returned Date when sent back and Hold Days for time pending clarification. | 1 per TSR
As they happen | Milestones | Add each milestone once. Set Forecast Date if it slips and Completed Date when done. | 1 per milestone
As they happen | Defect_Log | Raise a defect the day it is logged; set Resolved Date when fix + confirmation test is complete (or on rejection). | 1 per defect
Monthly / Quarterly | Weekly_Snapshot (CSAT columns) | Enter the CSAT score and number of responses only in the week a survey result is received; otherwise leave blank (= 'Not Requested'). | Occasional
Monthly / Quarterly | Demand_Forecast | Refresh planned vs available FTE for the coming months. | 1 per month
Monthly / Quarterly | Lessons_Learned | Record lessons and improvement actions; update Status when actioned. | As needed
Monthly / Quarterly | Resourcing | Update when people join, change allocation or leave. | As needed
Yearly / rarely | Bank_Holidays, Config, Lists | Extend bank holidays each year; change RAG thresholds or add dropdown values (Lists) only when the rules change. | Rare
3. Colour legend
Sample | Input cell (yellow, blue) | Type here or pick from the dropdown.
Sample | Calculated cell (grey) | Formula – never type over it.
Sample | EXAMPLE row (grey italic) | Delete it; the dashboard ignores rows whose Notes start with EXAMPLE.
Green | Green | On track / within target.
Amber | Amber | At risk / watch closely.
Red | Red | Off track / action needed.
4. Flow vs cumulative: how weeks roll up into a month or quarter
Type | Measures | Roll-up rule | Why
FLOW measures | Planned Test Days, Downtime Hours | SUM over the weeks in the period. | Each week records only what happened that week.
CUMULATIVE / snapshot measures | Coverage, automation, test execution (passed / failed / blocked, designed), resources, cumulative spend, forecast at completion | Take the LATEST week in the period. | Each week records the running total to date, so the last week already contains everything before it.
Example: September availability = 1 − (sum of September downtime hours) ÷ (sum of September planned test days × hours per test day). Coverage for September = the value in the last September week.
5. RAG rules the dashboard applies (thresholds live on the Config sheet)
KPI | Rule |  | Source
Risk Based Coverage | Per risk level: coverage = Covered ÷ Requirements; Green ≥ target, Amber ≥ target − tolerance, else Red. Overall = worst of High and Medium. |  | ATS KPI Data Collation – M.Coverage (3.9)
Production Defect Leakage (quarterly) | Defects with Found In = Production in the quarter to date. Red if P1 ≥ 1 or P2 ≥ 5 or P3 ≥ 6; Amber if P2 in 1–4 or P3 in 1–5; else Green. 'Not in Production' while Go-Live is blank. |  | Q.Defects (3.1)
Defect Detection Effectiveness | DDE = Testing-found ÷ (Testing-found + Production-found). Also raised / rejected by priority; rejection % Green ≤ 5%, Amber ≤ 10%, else Red. |  | M.Defects (3.2)
Defect Aging | Working-day aging buckets; SLA compliance = share resolved within SLA days; Green ≥ 80%, Amber ≥ 60%, else Red. |  | M.Defect Turnaround (4.11); thresholds are an ASSUMPTION
Automation Coverage (quarterly) | Green if ≥ target (95%) or improved vs the previous period, else Amber. |  | Q.Automation (4.5)
Milestone Delivery | Per milestone: completed on time = Green, completed late = Red; open and past due = Red; due within 5 days = Amber; else Green. Overall Red if any Red; Amber if share of Amber > 20%; else Green. |  | M.Test Milestone Delays (4.15)
Environment Availability | Downtime hours: monthly Green ≤ 24, Amber ≤ 48, else Red; weekly thresholds are set on Config. |  | M.Downtime (4.14); weekly thresholds are an ASSUMPTION
TSR Impact Assessment | Red if any TSR working days > SLA (10), else Green. |  | M.TSR Assessment (3.5)
Customer Satisfaction (quarterly) | Green if score ≥ pass mark and not declining; Red if < pass mark and not improving; else Amber. 'Not Requested' if blank. |  | Q.Satisfaction (3.3)
Resource Position | Actual ÷ Planned: Green ≥ 100%, Amber ≥ 90%, else Red. |  | ASSUMPTION
Demand Forecast | Planned FTE vs Available FTE for the next 3 months: Green if available ≥ planned; Amber if gap ≤ 1 FTE; else Red. |  | ASSUMPTION
Commercial Performance | Forecast vs Budget: Green ≤ budget; Amber ≤ budget + 5%; else Red. |  | ASSUMPTION
RAID Health | Red if any open risk/issue is rated Very High (score ≥ 20); Amber if any High (15–19); else Green. |  | ASSUMPTION (from the Test RAID Log)
Test Execution Progress | Blocked ÷ planned TCs: Green ≤ 5%, Amber ≤ 20%, else Red. |  | ASSUMPTION
SIT Readiness | Worst latest overall RAG across topics in Readiness (from your weekly rows). |  | Derived from the Readiness sheet
6. The EXAMPLE-row rule
• Every data sheet (except Bank_Holidays and Lists) has a Notes column as its LAST column. Rows whose Notes start with the word EXAMPLE are ignored by the dashboard.
• The blank template ships with one grey italic EXAMPLE row on each data sheet (Notes = “EXAMPLE – delete this row”). Overwrite or delete it when you add your first real row. If you forget, nothing breaks – it is simply skipped.
• The SAMPLE workbook has no example rows: its rows are made-up history made up for this portfolio.
7. How to load into the dashboard
• Save this file as ATS_Weekly_Data.xlsx (see section 8 for the portfolio folder layout). Keep the RAID log in its own existing file (ATS - Test RAID Log.xlsx format) and the plan in ATS_POAP.xlsx.
• Put all three files in the SAME folder.
• Open the dashboard and choose that folder in the load step; it reads the three workbooks offline and builds the Weekly Report and Monthly Council views.
• Weekly routine: open the file on Friday, add your rows, save, reload the folder in the dashboard. Check Config > Data Mode says LIVE before presenting.
8. Many portfolios, one design
• This workbook design is the same for EVERY portfolio. Each portfolio keeps its OWN copy: copy the template, set Portfolio Name (and Programme) on the Config sheet, then fill it weekly. Portfolio Name must be unique across portfolios.
• Recommended folder layout: ATS_Program/<Portfolio Name>/ATS_Weekly_Data.xlsx, with that portfolio's ATS_POAP.xlsx and RAID log in the same subfolder.
• Alternative: one flat folder with files named ATS_Weekly_Data - <Portfolio Name>.xlsx.
• In the dashboard: use Load program folder once and a portfolio dropdown appears. The Programme Overview compares all portfolios; Monthly Council, Weekly Report and POAP show the selected portfolio.
• A portfolio without a POAP or RAID file simply does not show those pages.

## Config
Config – programme details, thresholds and rules
Keys in column A are read by the dashboard (text must not change); edit only the yellow values in column B.
SAMPLE DATA – fictional illustrative history for this portfolio; replace before presenting
Setting | Value | Description / assumption
Program Name | HMRC ATS – Child Benefit | Shown in dashboard headers. SAMPLE – fictional value.
Project / Phase | Phase 1 | SAMPLE – fictional value for this portfolio.
TSR Reference | TSR_PR018102-REQ026544 | The portfolio's own TSR (QA activities and resource estimation). SAMPLE – dummy reference.
Programme Test Manager | TBC | SAMPLE – name left as TBC.
Test Manager | TBC | SAMPLE – name left as TBC.
Programme Start Date | 2026-02-02 | SAMPLE – fictional date.
Programme End Date | 2026-12-18 | Programme end date as supplied by the test-delivery lead.
Total Budget (£) | 310000 | SAMPLE – fictional budget scaled to the portfolio's size.
Production Go-Live Date | 2026-08-17 | Leave BLANK until the solution is live in production. Blank = 'Not in Production' (Production Defect Leakage is not scored).
Data Mode | SAMPLE | SAMPLE DATA – fictional illustrative history for this portfolio; replace before presenting. SAMPLE = seeded demo data; LIVE = real data. The dashboard shows a SAMPLE badge when this says SAMPLE. Change to LIVE once you replace the sample rows with real ones.
Hours per Test Day | 8 | Source: ATS KPI Data Collation – M.Downtime (4.14): Required Hours = test days x 8.
TSR SLA – Max Working Days | 10 | Source: ATS KPI Data Collation – M.TSR Assessment (3.5): Red if any TSR working days > 10.
Defect Turnaround SLA – Working Days | 5 | Source: M.Defect Turnaround (4.11) ageing buckets (0-2, 3-5, 6-10, >10 days). ASSUMPTION: not defined in the source KPI workbook; 5 working days is used as the SLA.
Defect Turnaround – Green if SLA compliance >= | 80% | ASSUMPTION – not defined in the source KPI workbook; turnaround RAG thresholds (share of defects resolved within SLA).
Defect Turnaround – Amber if SLA compliance >= | 60% | ASSUMPTION – not defined in the source KPI workbook; turnaround RAG thresholds (share of defects resolved within SLA).
Defect Rejection – Green if <= | 5% | Source: ATS KPI Data Collation – M.Defects (3.2): Green if rejection <= 5%.
Defect Rejection – Amber if <= | 10% | Source: ATS KPI Data Collation – M.Defects (3.2): Amber if rejection <= 10%, else Red.
Downtime (monthly) – Green if hours <= | 24 | Source: ATS KPI Data Collation – M.Downtime (4.14).
Downtime (monthly) – Amber if hours <= | 48 | Source: ATS KPI Data Collation – M.Downtime (4.14); above this = Red.
Downtime (weekly) – Green if hours <= | 6 | ASSUMPTION – not defined in the source KPI workbook; weekly downtime thresholds (monthly thresholds scaled to a week).
Downtime (weekly) – Amber if hours <= | 12 | ASSUMPTION – not defined in the source KPI workbook; weekly downtime thresholds; above this = Red.
Coverage Target – High Risk | 98% | Source: ATS KPI Data Collation – M.Coverage (3.9).
Coverage Target – Medium Risk | 95% | Source: ATS KPI Data Collation – M.Coverage (3.9).
Coverage Target – Low Risk | 0% | Source: ATS KPI Data Collation – M.Coverage (3.9) (no target for Low risk).
Coverage – Amber tolerance (points) | 2% | Source: M.Coverage (3.9): Amber if within 2 points below target (H >= -2%).
Milestone – Amber window (days before due) | 5 | Source: ATS KPI Data Collation – M.Test Milestone Delays (4.15): Amber if due within 5 days.
Milestone – Amber if share of Amber > | 20% | Source: M.Test Milestone Delays (4.15): overall Amber if more than 20% of milestones are Amber (Red if any Red).
Automation Target | 95% | Source: ATS KPI Data Collation – Q.Automation (4.5): Green if >= 95% or improved vs previous.
CSAT Pass Mark (1-5 score) | 3 | Source: ATS KPI Data Collation – Q.Satisfaction (3.3): pass mark 3.
Resource – Amber if actual >= (share of plan) | 90% | ASSUMPTION – not defined in the source KPI workbook; resource RAG: Green >= 100% of plan, Amber >= this share, else Red.
Execution – Amber if blocked share of planned > | 5% | ASSUMPTION – not defined in the source KPI workbook; the dashboard flags test execution RAG from blocked ÷ planned test cases.
Execution – Red if blocked share of planned > | 20% | ASSUMPTION – not defined in the source KPI workbook; the dashboard flags test execution RAG from blocked ÷ planned test cases.
Commercial – Amber if forecast <= budget + (share) | 5% | ASSUMPTION – not defined in the source KPI workbook; commercial RAG: Green <= budget, Amber <= budget + this share, else Red.
Portfolio Name | Child Benefit | The name this portfolio is shown under in the dashboard's portfolio dropdown and cross-portfolio overview. Must be unique across portfolios.
Programme | HMRC ATS | Groups portfolios under one programme heading.

## Weekly_Snapshot
Weekly_Snapshot [SAMPLE DATA – illustrative]
One row per week: environment, coverage, automation, satisfaction, resourcing & commercials and the overall RAG. Coverage / automation / resources / spend are CUMULATIVE to date.
HOW TO FILL: add ONE new row each Friday (new Week Ending). Yellow = type; grey = formula. Leave CSAT blank unless a score was collected that week.
WEEK | ENVIRONMENT |  |  | COVERAGE | [11 empty] | AUTOMATION | [5 empty] | SATISFACTION |  | RESOURCING & COMMERCIALS |  |  |  | OVERALL
Week Ending | Planned Test Days | Downtime Hours | Availability % | High Risk – Requirements | High Risk – Test Cases | High Risk – Covered Reqs | High Risk – Coverage % | Medium Risk – Requirements | Medium Risk – Test Cases | Medium Risk – Covered Reqs | Medium Risk – Coverage % | Low Risk – Requirements | Low Risk – Test Cases | Low Risk – Covered Reqs | Low Risk – Coverage % | Automatable Test Data Setups | Automated Test Data Setups | Test Data Automation % | Automatable Test Cases | Automated Test Cases | Test Case Automation % | CSAT Score (1-5) | CSAT Responses | Resources Planned (FTE) | Resources Actual (FTE) | Cumulative Spend (£) | Forecast at Completion (£) | Overall RAG | Overall Executive Summary | Notes
2026-07-10 | 5 | 0 | 100% | 60 | 21 | 21 | 35% | 80 | 23 | 23 | 28.75% | 30 | 8 | 8 | 26.67% | 100 | 45 | 45% | 150 | 60 | 40% |  |  | 5 | 5 | 212000 | 310000 | Green | Final pre-live regression cycles under way; test approach confirmed. Cumulative execution: 0 of 280 test cases (0%); 0 blocked; 0 open defects.
2026-07-17 | 5 | 1 | 97.5% | 60 | 28 | 28 | 46.67% | 80 | 33 | 33 | 41.25% | 30 | 16 | 11 | 36.67% | 100 | 49 | 49% | 150 | 65 | 43.33% |  |  | 5 | 5 | 216000 | 310000 | Green | Claims regression executed; first defects resolved within SLA. Cumulative execution: 0 of 280 test cases (0%); 0 blocked; 0 open defects.
2026-07-24 | 5 | 0 | 100% | 60 | 41 | 35 | 58.33% | 80 | 62 | 42 | 52.5% | 30 | 35 | 14 | 46.67% | 100 | 52 | 52% | 150 | 70 | 46.67% |  |  | 5 | 4 | 221000 | 310000 | Green | Payments testing in progress; one team member unavailable for a week. Cumulative execution: 36 of 280 test cases (13%); 0 blocked; 0 open defects.
2026-07-31 | 5 | 0 | 100% | 60 | 58 | 41 | 68.33% | 80 | 86 | 50 | 62.5% | 30 | 48 | 16 | 53.33% | 100 | 56 | 56% | 150 | 75 | 50% |  |  | 5 | 5 | 225000 | 310000 | Green | E2E rehearsal complete; go-live readiness review passed. Cumulative execution: 78 of 280 test cases (28%); 0 blocked; 0 open defects.
2026-08-07 | 5 | 1 | 97.5% | 60 | 62 | 46 | 76.67% | 80 | 93 | 58 | 72.5% | 30 | 51 | 18 | 60% | 100 | 59 | 59% | 150 | 80 | 53.33% |  |  | 5 | 5 | 230000 | 310000 | Green | Performance testing complete; go/no-go scheduled. Cumulative execution: 97 of 280 test cases (35%); 0 blocked; 1 open defect.
2026-08-14 | 5 | 0 | 100% | 60 | 62 | 50 | 83.33% | 80 | 93 | 64 | 80% | 30 | 51 | 20 | 66.67% | 100 | 63 | 63% | 150 | 85 | 56.67% |  |  | 5 | 5 | 234000 | 310000 | Green | Child Benefit services went live in production on 17 August 2026; hypercare started. Cumulative execution: 113 of 280 test cases (40%); 0 blocked; 0 open defects. | Go-live 17 August 2026.
2026-08-21 | 5 | 0 | 100% | 60 | 64 | 53 | 88.33% | 80 | 96 | 68 | 85% | 30 | 54 | 21 | 70% | 100 | 66 | 66% | 150 | 90 | 60% |  |  | 5 | 5 | 239000 | 310000 | Green | Hypercare: no production incidents; regression pack running. Cumulative execution: 127 of 280 test cases (45%); 0 blocked; 0 open defects.
2026-08-28 | 5 | 1 | 97.5% | 60 | 66 | 56 | 93.33% | 80 | 99 | 72 | 90% | 30 | 54 | 22 | 73.33% | 100 | 70 | 70% | 150 | 95 | 63.33% | 3.9 | 38 | 5 | 5 | 243000 | 310000 | Green | First CSAT survey result received (3.9 out of 5); Enhancements Release 3 test design under way. Cumulative execution: 139 of 280 test cases (50%); 0 blocked; 0 open defects. | CSAT survey 1 (38 responses).
2026-09-04 | 5 | 0 | 100% | 60 | 70 | 58 | 96.67% | 80 | 104 | 74 | 92.5% | 30 | 58 | 23 | 76.67% | 100 | 72 | 72% | 150 | 100 | 66.67% |  |  | 5 | 5 | 248000 | 310000 | Green | Hypercare closed; Release 3 design progressing. Cumulative execution: 149 of 280 test cases (53%); 0 blocked; 0 open defects.
2026-09-11 | 5 | 1 | 97.5% | 60 | 74 | 59 | 98.33% | 80 | 111 | 76 | 95% | 30 | 62 | 24 | 80% | 100 | 75 | 75% | 150 | 105 | 70% |  |  | 5 | 5 | 252000 | 310000 | Green | Production defect (P2) found in claim processing; fixed and confirmed within 4 days. Cumulative execution: 160 of 280 test cases (57%); 0 blocked; 0 open defects.
2026-09-18 | 5 | 0 | 100% | 60 | 79 | 59 | 98.33% | 80 | 118 | 77 | 96.25% | 30 | 65 | 24 | 80% | 100 | 77 | 77% | 150 | 110 | 73.33% |  |  | 5 | 5 | 257000 | 310000 | Green | Release 3 SIT started; no open defects. Cumulative execution: 180 of 280 test cases (64%); 0 blocked; 0 open defects.
2026-09-25 | 5 | 0 | 100% | 60 | 82 | 60 | 100% | 80 | 124 | 78 | 97.5% | 30 | 69 | 24 | 80% | 100 | 80 | 80% | 150 | 115 | 76.67% | 4.2 | 42 | 5 | 5 | 261000 | 310000 | Green | Second CSAT survey result 4.2 out of 5, up from 3.9. A minor P3 production defect was resolved. Cumulative execution: 201 of 280 test cases (72%); 0 blocked; 0 open defects. | CSAT survey 2 (42 responses).
2026-10-02 | 5 | 1 | 97.5% | 60 | 84 | 60 | 100% | 80 | 126 | 78 | 97.5% | 30 | 70 | 24 | 80% | 100 | 82 | 82% | 150 | 120 | 80% |  |  | 5 | 5 | 266000 | 310000 | Green | Portfolio remains Green: services stable in production, Release 3 testing on plan; demand forecast shows an FTE gap from November. Cumulative execution: 221 of 280 test cases (79%); 0 blocked; 0 open defects.

## Topic_Progress
Topic_Progress [SAMPLE DATA – illustrative]
One row per topic per week. All counts are CUMULATIVE to date at that Week Ending.
HOW TO FILL: each Friday add one row for every active topic; pick Topic and Phase from the dropdowns. Executed and % columns calculate themselves.
Week Ending | Topic | Phase | TCs Planned | TCs Designed | Passed | Failed | Blocked | Executed | % Executed | % Designed | Comments | Notes
2026-07-10 | Child Benefit – Claims Service | Test Prep | 110 | 11 | 0 | 0 | 0 | 0 | 0% | 10% | Test design 10% complete.
2026-07-17 | Child Benefit – Claims Service | SIT | 110 | 37 | 0 | 0 | 0 | 0 | 0% | 33.64% | Test design 34% complete.
2026-07-24 | Child Benefit – Claims Service | SIT | 110 | 84 | 35 | 1 | 0 | 36 | 32.73% | 76.36% | 36 executed (35 passed, 1 failed); 0 blocked.
2026-07-31 | Child Benefit – Claims Service | E2E | 110 | 110 | 47 | 2 | 0 | 49 | 44.55% | 100% | 49 executed (47 passed, 2 failed); 0 blocked.
2026-08-07 | Child Benefit – Claims Service | E2E | 110 | 110 | 56 | 2 | 0 | 58 | 52.73% | 100% | 58 executed (56 passed, 2 failed); 0 blocked.
2026-08-14 | Child Benefit – Claims Service | E2E | 110 | 110 | 63 | 3 | 0 | 66 | 60% | 100% | 66 executed (63 passed, 3 failed); 0 blocked.
2026-08-21 | Child Benefit – Claims Service | Regression | 110 | 110 | 70 | 3 | 0 | 73 | 66.36% | 100% | 73 executed (70 passed, 3 failed); 0 blocked.
2026-08-28 | Child Benefit – Claims Service | Regression | 110 | 110 | 77 | 3 | 0 | 80 | 72.73% | 100% | 80 executed (77 passed, 3 failed); 0 blocked.
2026-09-04 | Child Benefit – Claims Service | Regression | 110 | 110 | 82 | 3 | 0 | 85 | 77.27% | 100% | 85 executed (82 passed, 3 failed); 0 blocked.
2026-09-11 | Child Benefit – Claims Service | Regression | 110 | 110 | 87 | 4 | 0 | 91 | 82.73% | 100% | 91 executed (87 passed, 4 failed); 0 blocked.
2026-09-18 | Child Benefit – Claims Service | Regression | 110 | 110 | 91 | 4 | 0 | 95 | 86.36% | 100% | 95 executed (91 passed, 4 failed); 0 blocked.
2026-09-25 | Child Benefit – Claims Service | Regression | 110 | 110 | 96 | 4 | 0 | 100 | 90.91% | 100% | 100 executed (96 passed, 4 failed); 0 blocked.
2026-10-02 | Child Benefit – Claims Service | Regression | 110 | 110 | 100 | 4 | 0 | 104 | 94.55% | 100% | 104 executed (100 passed, 4 failed); 0 blocked.
2026-07-10 | Child Benefit – Payments | Test Prep | 90 | 9 | 0 | 0 | 0 | 0 | 0% | 10% | Test design 10% complete.
2026-07-17 | Child Benefit – Payments | Test Prep | 90 | 22 | 0 | 0 | 0 | 0 | 0% | 24.44% | Test design 24% complete.
2026-07-24 | Child Benefit – Payments | Test Prep | 90 | 50 | 0 | 0 | 0 | 0 | 0% | 55.56% | Test design 56% complete.
2026-07-31 | Child Benefit – Payments | SIT | 90 | 77 | 28 | 1 | 0 | 29 | 32.22% | 85.56% | 29 executed (28 passed, 1 failed); 0 blocked.
2026-08-07 | Child Benefit – Payments | SIT | 90 | 90 | 37 | 2 | 0 | 39 | 43.33% | 100% | 39 executed (37 passed, 2 failed); 0 blocked.
2026-08-14 | Child Benefit – Payments | E2E | 90 | 90 | 45 | 2 | 0 | 47 | 52.22% | 100% | 47 executed (45 passed, 2 failed); 0 blocked.
2026-08-21 | Child Benefit – Payments | Regression | 90 | 90 | 52 | 2 | 0 | 54 | 60% | 100% | 54 executed (52 passed, 2 failed); 0 blocked.
2026-08-28 | Child Benefit – Payments | Regression | 90 | 90 | 57 | 2 | 0 | 59 | 65.56% | 100% | 59 executed (57 passed, 2 failed); 0 blocked.
2026-09-04 | Child Benefit – Payments | Regression | 90 | 90 | 61 | 3 | 0 | 64 | 71.11% | 100% | 64 executed (61 passed, 3 failed); 0 blocked.
2026-09-11 | Child Benefit – Payments | Regression | 90 | 90 | 66 | 3 | 0 | 69 | 76.67% | 100% | 69 executed (66 passed, 3 failed); 0 blocked.
2026-09-18 | Child Benefit – Payments | Regression | 90 | 90 | 70 | 3 | 0 | 73 | 81.11% | 100% | 73 executed (70 passed, 3 failed); 0 blocked.
2026-09-25 | Child Benefit – Payments | Regression | 90 | 90 | 74 | 3 | 0 | 77 | 85.56% | 100% | 77 executed (74 passed, 3 failed); 0 blocked.
2026-10-02 | Child Benefit – Payments | Regression | 90 | 90 | 78 | 3 | 0 | 81 | 90% | 100% | 81 executed (78 passed, 3 failed); 0 blocked.
2026-08-21 | Child Benefit – Enhancements Release 3 | Test Prep | 80 | 8 | 0 | 0 | 0 | 0 | 0% | 10% | Test design 10% complete.
2026-08-28 | Child Benefit – Enhancements Release 3 | Test Prep | 80 | 13 | 0 | 0 | 0 | 0 | 0% | 16.25% | Test design 16% complete.
2026-09-04 | Child Benefit – Enhancements Release 3 | Test Prep | 80 | 25 | 0 | 0 | 0 | 0 | 0% | 31.25% | Test design 31% complete.
2026-09-11 | Child Benefit – Enhancements Release 3 | Test Prep | 80 | 40 | 0 | 0 | 0 | 0 | 0% | 50% | Test design 50% complete.
2026-09-18 | Child Benefit – Enhancements Release 3 | Smoke | 80 | 55 | 12 | 0 | 0 | 12 | 15% | 68.75% | 12 executed (12 passed, 0 failed); 0 blocked.
2026-09-25 | Child Benefit – Enhancements Release 3 | SIT | 80 | 67 | 23 | 1 | 0 | 24 | 30% | 83.75% | 24 executed (23 passed, 1 failed); 0 blocked.
2026-10-02 | Child Benefit – Enhancements Release 3 | SIT | 80 | 72 | 35 | 1 | 0 | 36 | 45% | 90% | 36 executed (35 passed, 1 failed); 0 blocked.

## Defect_Log
Defect_Log [SAMPLE DATA – illustrative]
One row per defect. Aging is in working days (inclusive) from Raised Date to Resolved Date (or today while open).
HOW TO FILL: add each defect when raised; set Resolved Date when fix + confirmation test is complete (or on rejection). Aging and bucket calculate themselves.
Defect ID | Summary | Topic | Test Type | Priority | Severity | Raised Date | Resolved Date | Status | Found In | Owner / DG | TCs Blocked | Triage Comments | Aging (Working Days) | Aging Bucket | Notes
CB-101 | Claim submission – message queued but not delivered | Child Benefit – Claims Service | SIT | P2 Medium | 3 - High | 2026-07-08 | 2026-07-10 | Closed | Testing | Dev Team 2 | 0 | Fix delivered and confirmed by retest. | 3 | 3-5 Days
CB-102 | Award calculation – wrong role permissions applied | Child Benefit – Claims Service | SIT | P1 High | 3 - High | 2026-07-14 | 2026-07-17 | Closed | Testing | Integration Team | 1 | Fix delivered and confirmed by retest. | 4 | 3-5 Days
CB-103 | Bank account change – message queued but not delivered | Child Benefit – Payments | SIT | P3 Low | 6 - Trivial | 2026-07-16 | 2026-07-17 | Closed | Testing | Data Team | 0 | Fix delivered and confirmed by retest. | 2 | 0-2 Days
CB-104 | Bank account change – field truncated in output | Child Benefit – Claims Service | SIT | P2 Medium | 4 - Standard | 2026-07-22 | 2026-07-24 | Resolved | Testing | Environments | 0 | Fix delivered and confirmed by retest. | 3 | 3-5 Days
CB-105 | Change of circumstances – incorrect date applied | Child Benefit – Claims Service | SIT | P3 Low | 5 - Low | 2026-07-30 | 2026-07-31 | Closed | Testing | Supplier A | 0 | Fix delivered and confirmed by retest. | 2 | 0-2 Days
CB-106 | Change of circumstances – unable to save amendments | Child Benefit – Payments | Smoke | P2 Medium | 4 - Standard | 2026-08-05 | 2026-08-11 | Closed | Testing | Dev Team 1 | 0 | Fix delivered and confirmed by retest. | 5 | 3-5 Days
CB-107 | Bank account change – error returned for valid input | Child Benefit – Payments | Smoke | P3 Low | 6 - Trivial | 2026-08-13 | 2026-08-14 | Closed | Testing | Dev Team 2 | 0 | Fix delivered and confirmed by retest. | 2 | 0-2 Days
CB-108 | Reconciliation report – layout breaks on small screens | Child Benefit – Payments | SIT | P3 Low | 6 - Trivial | 2026-08-27 | 2026-08-28 | Resolved | Testing | Integration Team | 0 | Fix delivered and confirmed by retest. | 2 | 0-2 Days
CB-109 | Bank account change – incorrect date applied | Child Benefit – Claims Service | Production | P2 Medium | 4 - Standard | 2026-09-08 | 2026-09-11 | Closed | Production | Live Support | 0 | Hotfix deployed and confirmed in production. | 4 | 3-5 Days
CB-110 | High Income Charge – totals do not reconcile | Child Benefit – Payments | SIT | P3 Low | 6 - Trivial | 2026-09-16 | 2026-09-18 | Closed | Testing | Environments | 0 | Fix delivered and confirmed by retest. | 3 | 3-5 Days
CB-111 | Bank account change – unable to save amendments | Child Benefit – Claims Service | Production | P3 Low | 6 - Trivial | 2026-09-21 | 2026-09-24 | Closed | Production | Live Support | 0 | Hotfix deployed and confirmed in production. | 4 | 3-5 Days
Formulas:
Aging (Working Days) = IF(OR([Defect ID]="",[Raised Date]=""),"",MAX(1,NETWORKDAYS([Raised Date],IF([Resolved Date]="",TODAY(),[Resolved Date]),Bank_Holidays!$A6:A60)))

## TSR_Log
TSR_Log [SAMPLE DATA – illustrative]
One row per Technical Service Request (TSR) received for impact assessment. Work Days exclude Hold Days.
HOW TO FILL: add the TSR when received; fill Returned Date when sent back to the Front Desk and Hold Days for time pending clarification.
TSR Ref | Description | Topic | Received Date | Returned Date | Hold Days (pending clarification) | Status | Value (£) | Work Days | Over SLA? | Notes
TSR_PR018102-REQ026544 | Raised for the portfolio's QA activities and resource estimation (the portfolio's own TSR). | Programme (cross-cutting) | 2026-01-19 | 2026-01-23 | 0 | Returned | 310000 | 5 | No
TSR_PR018655-REQ027301 | Test impact assessment for a payments change. | Programme (cross-cutting) | 2026-05-11 | 2026-05-18 | 0 | Returned |  | 6 | No
PR019420-REQ027988 | Follow-on test estimate; returned after a scope clarification. | Programme (cross-cutting) | 2026-07-13 | 2026-07-17 | 1 | Returned |  | 4 | No
TSR_PR021340-REQ031020 | Test impact assessment for a production support change. | Programme (cross-cutting) | 2026-09-01 | 2026-09-09 | 0 | Returned |  | 7 | No
PR022790-REQ033315 | Test impact assessment for a further change; assessment in progress. | Programme (cross-cutting) | 2026-09-29 |  | 0 | Open |  | 4 | No
Formulas:
Work Days = IF(OR([TSR Ref]="",[Received Date]=""),"",MAX(0,NETWORKDAYS([Received Date],IF([Returned Date]="",TODAY(),[Returned Date]),Bank_Holidays!$A6:A60)-N([Hold Days (pending clarification)])))

## Milestones
Milestones [SAMPLE DATA – illustrative]
One row per test milestone with due, forecast and completed dates. Delay, status and RAG calculate against today's date.
HOW TO FILL: add each milestone once; set Forecast Date if it slips and Completed Date when done. Critical? = Yes for key milestones.
Milestone | Topic | Due Date | Forecast Date | Completed Date | Owner | Critical? | Delay (Days) | Status | RAG | Notes
Test Approach | Programme (cross-cutting) | 2026-02-27 |  | 2026-02-26 | Programme Test Manager | Yes | 0 | Completed | Green
Smoke Testing | Child Benefit – Claims Service | 2026-04-02 |  | 2026-04-01 | Test Manager | Yes | 0 | Completed | Green
SIT Test Script Creation | Child Benefit – Claims Service | 2026-05-15 |  | 2026-05-14 | Test Lead | Yes | 0 | Completed | Green
E2E Test Script Creation | Child Benefit – Claims Service | 2026-06-12 |  | 2026-06-11 | Test Lead | Yes | 0 | Completed | Green
SIT Test Script Execution – Phase 1 | Child Benefit – Claims Service | 2026-07-17 |  | 2026-07-16 | Test Manager | Yes | 0 | Completed | Green
SIT Test Script Execution – Phase 2 | Child Benefit – Claims Service | 2026-08-07 |  | 2026-08-06 | Test Manager | No | 0 | Completed | Green
NFR Test Scripts Ready | Child Benefit – Claims Service | 2026-07-24 |  | 2026-07-24 | Test Lead | No | 0 | Completed | Green
Automation of Smoke / Regression Testing | Programme (cross-cutting) | 2026-10-30 |  |  | Automation Engineer 1 | No | 0 | On Schedule | Green
E2E Test Script Execution | Child Benefit – Claims Service | 2026-08-14 |  | 2026-08-13 | Test Manager | No | 0 | Completed | Green
Defect Retest Cycle 1 Complete | Child Benefit – Claims Service | 2026-09-11 |  | 2026-09-10 | Test Manager | No | 0 | Completed | Green
Test Completion Report | Programme (cross-cutting) | 2026-12-11 |  |  | Programme Test Manager | No | 0 | On Schedule | Green
Formulas:
Delay (Days) = IF(OR([Milestone]="",[Due Date]=""),"",IF([Completed Date]<>"",MAX(0,[Completed Date]-[Due Date]),MAX(0,TODAY()-[Due Date])))
Status = IF(OR([Milestone]="",[Due Date]=""),"",IF([Completed Date]<>"",IF([Completed Date]<=[Due Date],"Completed","Completed Late"),IF(TODAY()>[Due Date],"Overdue","On Schedule")))
RAG = IF(OR([Milestone]="",[Due Date]=""),"",IF([Completed Date]<>"",IF([Completed Date]<=[Due Date],"Green","Red"),IF(TODAY()>[Due Date],"Red",IF([Due Date]-TODAY()<=Config!$B30,"Amber","Green"))))

## Readiness
Readiness [SAMPLE DATA – illustrative]
SIT readiness per topic per week: overall RAG, six readiness areas (RAG + note) and the road to Green.
HOW TO FILL: each Friday add one row per topic still in preparation; pick RAG from the dropdowns and use short notes (Alt+Enter for new lines).
Week Ending | Topic | Planned SIT Start | Overall RAG | Requirements & Arch Intent RAG | Requirements & Arch Intent – Note | Blockers RAG | Blockers – Note | Resources RAG | Resources – Note | Environments RAG | Environments – Note | Test Scripts & Test Data RAG | Test Scripts & Test Data – Note | Knowledge Transfer RAG | Knowledge Transfer – Note | Road to Green | Notes
2026-09-11 | Child Benefit – Payments | 2026-10-05 | Green | Green | Requirements baselined and reviewed. | Green | N/A | Green | Resources in place. | Green | Test environment ready. | Green | Scripts and test data on plan. | Green | Knowledge transfer complete.
2026-09-11 | Child Benefit – Enhancements Release 3 | 2026-11-02 | Green | Green | Requirements baselined and reviewed. | Green | N/A | Green | Resources in place. | Green | Test environment ready. | Green | Scripts and test data on plan. | Green | Knowledge transfer complete.
2026-09-18 | Child Benefit – Payments | 2026-10-05 | Green | Green | Requirements baselined and reviewed. | Green | N/A | Green | Resources in place. | Green | Test environment ready. | Green | Scripts and test data on plan. | Green | Knowledge transfer complete.
2026-09-18 | Child Benefit – Enhancements Release 3 | 2026-11-02 | Green | Green | Requirements baselined and reviewed. | Green | N/A | Green | Resources in place. | Green | Test environment ready. | Green | Scripts and test data on plan. | Green | Knowledge transfer complete.
2026-09-25 | Child Benefit – Payments | 2026-10-05 | Green | Green | Requirements baselined and reviewed. | Green | N/A | Green | Resources in place. | Green | Test environment ready. | Green | Scripts and test data on plan. | Green | Knowledge transfer complete.
2026-09-25 | Child Benefit – Enhancements Release 3 | 2026-11-02 | Green | Green | Requirements baselined and reviewed. | Green | N/A | Green | Resources in place. | Green | Test environment ready. | Green | Scripts and test data on plan. | Green | Knowledge transfer complete.
2026-10-02 | Child Benefit – Payments | 2026-10-05 | Green | Green | Requirements baselined and reviewed. | Green | N/A | Green | Resources in place. | Green | Test environment ready. | Green | Scripts and test data on plan. | Green | Knowledge transfer complete.
2026-10-02 | Child Benefit – Enhancements Release 3 | 2026-11-02 | Green | Green | Requirements baselined and reviewed. | Green | N/A | Green | Resources in place. | Green | Test environment ready. | Green | Scripts and test data on plan. | Green | Knowledge transfer complete.

## Commentary
Commentary [SAMPLE DATA – illustrative]
Optional narrative per KPI per week (Key Highlights / Area of Concern / Actions Underway / Executive Commentary).
HOW TO FILL: add a row for any KPI you want to explain this week (KPI from dropdown); separate bullets with Alt+Enter. RAG Override only if you disagree with the calculated RAG.
Week Ending | KPI | Key Highlights | Area of Concern | Actions Underway | Executive Commentary | RAG Override | Current Position Override | Notes
2026-09-25 | Overall | Services are live and stable; CSAT improved from 3.9 to 4.2. Execution of the Release 3 enhancements has started on plan. | Two production defects (1 P2, 1 P3) were found in September, both fixed. Demand forecast shows 10 FTE needed against 8 available from November. | Add regression scripts for the affected journeys; confirm 2 additional FTE for Enhancements Release 3. | The portfolio remains Green. Quality is good and customer satisfaction is improving. The two production defects were fixed quickly and the capacity gap from November needs a resourcing decision. |  |  | SAMPLE

## Resourcing
Resourcing [SAMPLE DATA – illustrative]
The team roster: role, name, organisation, allocation, dates and status.
HOW TO FILL: add a row when someone joins or is planned; set End Date and Status = Left when they leave. Do not delete history.
Role | Name | Organisation | Allocation % | Start Date | End Date | Status | Notes
Programme Test Manager | TBC | Delivery Partner | 100% | 2026-02-02 |  | Active | Name placeholder – SAMPLE.
Test Manager | TBC | Delivery Partner | 100% | 2026-02-02 |  | Active | Name placeholder – SAMPLE.
Test Lead | TBC | Delivery Partner | 100% | 2026-02-02 |  | Active | Name placeholder – SAMPLE.
Senior Test Analyst 1 | TBC | Delivery Partner | 100% | 2026-02-09 |  | Active | Name placeholder – SAMPLE.
Test Analyst 1 | TBC | Delivery Partner | 100% | 2026-02-09 |  | Active | Name placeholder – SAMPLE.
Test Analyst 2 | TBC | Delivery Partner | 100% | 2026-12-28 |  | Planned | Planned uplift. Name placeholder – SAMPLE.

## Demand_Forecast
Demand_Forecast [SAMPLE DATA – illustrative]
Forward view of Planned vs Available FTE by month (Month = first day of the month).
HOW TO FILL: refresh monthly: one row per future month, Month entered as the 1st of the month.
Month | Planned FTE | Available FTE | Notes
2026-07-01 | 5 | 5 | Capacity aligned to demand.
2026-08-01 | 5 | 5 | Capacity aligned to demand.
2026-09-01 | 5 | 5 | Capacity aligned to demand.
2026-10-01 | 5 | 5 | Capacity aligned to demand.
2026-11-01 | 10 | 8 | 2 FTE gap; recruitment / onboarding decision needed.
2026-12-01 | 10 | 8 | 2 FTE gap; recruitment / onboarding decision needed.
2027-01-01 | 10 | 8 | 2 FTE gap; recruitment / onboarding decision needed.
2027-02-01 | 10 | 8 | 2 FTE gap; recruitment / onboarding decision needed.
2027-03-01 | 8 | 8 | Capacity aligned to demand.

## Lessons_Learned
Lessons_Learned [SAMPLE DATA – illustrative]
Lessons learned and the improvement action agreed for each.
HOW TO FILL: add a row per lesson; update Status to Actioned when the improvement is in place.
Date | Category | Lesson Learned | Improvement Action | Owner | Status | Notes
2026-08-24 | Release | A staged hypercare with daily checks caught issues before customers reported them. | Reuse the hypercare checklist for Enhancements Release 3. | Test Manager | Actioned | SAMPLE
2026-09-14 | Test Coverage | A P2 production defect was in a path with no regression script. | Add the path to the regression pack and review other low-volume journeys. | Test Lead | Open | SAMPLE

## Bank_Holidays
Bank_Holidays [reference data]
England & Wales bank holidays used by the working-day (NETWORKDAYS) calculations. Source: ATS - KPIs - Data Collation.xlsx > Bank Holidays.
HOW TO FILL: extend yearly – add next year's dates below the last row (rows 6–60 are used by the formulas).
Date | Name
2026-01-01 | New Year’s Day
2026-04-03 | Good Friday
2026-04-06 | Easter Monday
2026-05-04 | Early May Bank Holiday
2026-05-25 | Spring Bank Holiday
2026-08-31 | Summer Bank Holiday
2026-12-25 | Christmas Day
2026-12-28 | Boxing Day (substitute for Saturday, 26 December)
2027-01-01 | New Year’s Day
2027-03-26 | Good Friday
2027-03-29 | Easter Monday
2027-05-03 | Early May Bank Holiday
2027-05-31 | Spring Bank Holiday
2027-08-30 | Summer Bank Holiday
2027-12-27 | Christmas Day (substitute for Saturday, 25 December)
2027-12-28 | Boxing Day (substitute for Sunday, 26 December)

## Lists
Priority | Severity | Test Type | Defect Status | Found In | TSR Status | RAG | Yes/No | Phase | Resource Status | Lesson Status | Topic | KPI
P1 High | 1 - Urgent | Smoke | Open | Testing | Open | Green | Yes | Test Prep | Active | Open | Child Benefit – Claims Service | Overall
P2 Medium | 2 - Very High | SIT | In Progress | Production | Returned | Amber | No | Smoke | Planned | Actioned | Child Benefit – Payments | Risk Based Coverage
P3 Low | 3 - High | E2E | Re-Open |  | Withdrawn | Red |  | SIT | Left |  | Child Benefit – Enhancements Release 3 | Production Defect Leakage
| 4 - Standard | NFR | Resolved |  |  |  |  | Regression |  |  | Programme (cross-cutting) | Defect Detection Effectiveness
| 5 - Low | Regression | Closed |  |  |  |  | E2E |  |  |  | Defect Aging
| 6 - Trivial | Production | Rejected |  |  |  |  | NFR |  |  |  | Automation Coverage
|  |  | Deferred |  |  |  |  | TCR / Sign-off |  |  |  | Milestone Delivery
Environment Availability
TSR Impact Assessment
Customer Satisfaction (CSAT)
Resource Position
Demand Forecast
Commercial Performance
RAID Health
Test Execution Progress
SIT Readiness
Dropdowns read rows 2–40 of each column. Add new values in the yellow cells below the last item of a list; keep the header text as is.