## Guide
ATS Plan on a Page (POAP) workbook
Fill this workbook once, drop it into the ATS Dashboard (POAP section) and it renders a filterable roadmap, an executive Plan-on-a-Page and the integration-flow matrix.
SAMPLE – fictional data (dates as at 2026-10-02). System names, topics and slips are invented for demonstration.
HOW TO USE
1. POAP_Config | Set program name, plan start/end and (optionally) a status date. Leave the status date blank to use today's date. Set Data Mode to LIVE for real data (SAMPLE shows a ribbon in the dashboard). Edit pillar/activity colours if you like (hex, no #).
2. POAP_Plan | One row per BAR on the roadmap. Pillar > Topic is the swimlane; Activity Type picks the colour and the phase on the Plan on a Page. Start/End are real dates. Baseline = the originally agreed dates (the dashboard draws a ghost bar and a +Nd slip badge when End moves past Baseline End). % Complete is 0-100% (0-1 also accepted).
Depends On: comma-separated IDs from column A (e.g. P1-004, P1-007) - the dashboard draws dependency arrows. Status 'Dates TBC': leave Start/End blank (or give an indicative date) and the bar shows hatched / in the TBC strip. Duration and Slip are calculated (grey) - do not type in them.
3. POAP_Milestones | Key dates shown as diamonds on the roadmap lane and in the Plan on a Page milestone strip.
4. P2P_Matrix | Point-to-point integration flows. System Path uses ' → ' between systems (also accepts -> or >). Record the result of each response class (2xx/3xx/4xx/5xx) from the dropdowns.
5. Lists | Dropdown values. Add values at the bottom of a list only if you also extend the matching colour table in POAP_Config.
COLOURS
Yellow cells / blue text | Inputs you type or paste.
Grey cells | Calculated - leave alone.
Grey italic row | EXAMPLE rows (Notes start with 'EXAMPLE') are ignored by the dashboard - overwrite or delete them.
STATUS RULES OF THUMB
Complete | End date in the past or work signed off; set % Complete to 100%.
Delayed | End has moved later than Baseline End; set RAG Amber/Red and explain in Notes.
Dates TBC | Dates not yet agreed; shown dashed/hatched and listed in the 'At risk / slipping' panel.

## POAP_Config
POAP Configuration
SAMPLE – fictional data. Global settings, pillar colours and activity-type colours used by the dashboard.
HOW TO FILL: edit the yellow cells only. Colours are hex without the # sign.
Setting | Value | Description
Program Name | HMRC ATS – Self Assessment (SAMPLE) | Shown in the top strip of the POAP section.
Plan Start Date | 2026-06-01 | Left edge of the roadmap (blank = earliest bar).
Plan End Date | 2027-06-30 | Right edge of the roadmap (blank = latest bar).
Status Date (blank = today) | 2026-10-02 | 'As at' date used for the today line, KPIs and Next 30 days.
Data Mode | SAMPLE | SAMPLE shows a ribbon in the dashboard; use LIVE for real data.
PILLARS
Pillar | Colour (hex, no #)
Pillar A – Returns | 2563EB
Pillar B – Payments | 0EA5A0
ACTIVITY TYPES
Activity Type | Colour (hex, no #)
Test Prep | 8B9DF8
Dependencies | C2A878
Regression | 0EA5E9
SIT | 3B5BDB
Smoke / P2P | 06B6D4
Defect Retest | E86AA6
TCR / Sign-off | 0F766E
E2E | 7C3AED
NFR | C084FC
Automation | 475569
Holiday / Freeze | CBD5E1
Other | 94A3B8

## POAP_Plan
POAP - Plan (one row per roadmap bar)
SAMPLE – fictional data. Each row is a bar on the roadmap: Pillar > Topic swimlane, coloured by Activity Type.
HOW TO FILL: yellow = input, grey = calculated. Dates as yyyy-mm-dd. Depends On = comma-separated IDs. Baseline = originally agreed dates (drives the slip badge).
IDENTITY |  |  |  |  | CURRENT DATES |  | BASELINE |  | PROGRESS & LINKS |  |  |  |  | SCOPE | CALCULATED |  | ADMIN
ID | Pillar | Topic | Activity Type | Item | Start | End | Baseline Start | Baseline End | % Complete | Status | RAG | Owner | Depends On | Scope / Notes | Duration (Days) | Slip (Days) | Notes
A-001 | Pillar A – Returns | Self Assessment – Release 1 | Test Prep | Test design & scripting | 2026-06-15 | 2026-07-31 | 2026-06-15 | 2026-07-31 | 100% | Complete | Green | Test Manager |  | Design and peer-review of release test scenarios. | 47 | 0
A-002 | Pillar A – Returns | Self Assessment – Release 1 | Dependencies | Test environment & data readiness | 2026-07-13 | 2026-08-07 | 2026-07-13 | 2026-08-07 | 100% | Complete | Green | Portfolio Test Lead | A-001 | Environment build, masked test data load and access set-up. | 26 | 0
A-003 | Pillar A – Returns | Self Assessment – Release 1 | Smoke / P2P | Smoke & connectivity checks | 2026-08-03 | 2026-08-12 | 2026-08-03 | 2026-08-12 | 100% | Complete | Green | Test Manager | A-002 | Portal to API Gateway to Ledger connectivity smoke. | 10 | 0
A-004 | Pillar A – Returns | Self Assessment – Release 1 | SIT | SIT Cycle 1 execution | 2026-08-13 | 2026-10-30 | 2026-08-13 | 2026-10-30 | 65% | In Progress | Green | Test Manager | A-003 | Functional system integration test, first cycle. | 79 | 0
A-005 | Pillar A – Returns | Self Assessment – Release 1 | Defect Retest | Defect retest – Cycle 1 | 2026-10-12 | 2026-11-13 | 2026-10-12 | 2026-11-13 | 0% | Not Started | Green | Test Manager | A-004 | Retest of fixes delivered during Cycle 1. | 33 | 0
A-006 | Pillar A – Returns | Self Assessment – Release 1 | SIT | SIT Cycle 2 execution | 2026-11-16 | 2026-12-18 | 2026-11-16 | 2026-12-18 | 0% | Not Started | Green | Test Manager | A-005 | Second cycle incl. fix verification and new scope. | 33 | 0
A-007 | Pillar A – Returns | Self Assessment – Release 1 | Regression | Regression pack execution | 2027-01-11 | 2027-02-05 | 2027-01-11 | 2027-02-05 | 0% | Not Started | Green | Test Manager | A-006, A-014 | Full regression of in-scope journeys. | 26 | 0
A-008 | Pillar A – Returns | Self Assessment – Release 1 | TCR / Sign-off | SIT exit report & TCR | 2027-02-08 | 2027-02-19 | 2027-02-08 | 2027-02-19 | 0% | Not Started | Green | Portfolio Test Lead | A-007 | Test completion report and SIT sign-off. | 12 | 0
A-009 | Pillar A – Returns | Self Assessment – Release 1 | E2E | End-to-end journey testing | 2027-02-22 | 2027-03-26 | 2027-02-22 | 2027-03-26 | 0% | Not Started | Green | Test Manager | A-008 | Cross-system journeys across the portfolio. | 33 | 0
A-010 | Pillar A – Returns | Self Assessment – Release 1 | NFR | Performance & resilience testing | 2027-03-01 | 2027-04-02 | 2027-03-01 | 2027-04-02 | 0% | Not Started | Green | Test Manager | A-009 | Load, soak and failover tests on a production-like set-up. | 33 | 0
A-011 | Pillar A – Returns | Self Assessment – Release 1 | Defect Retest | Defect retest – E2E | 2027-03-29 | 2027-04-16 | 2027-03-29 | 2027-04-16 | 0% | Not Started | Green | Test Manager | A-010 | Retest of E2E and NFR defect fixes. | 19 | 0
A-012 | Pillar A – Returns | Self Assessment – Release 1 | TCR / Sign-off | E2E sign-off | 2027-04-19 | 2027-04-30 | 2027-04-19 | 2027-04-30 | 0% | Not Started | Green | Portfolio Test Lead | A-011 | E2E test completion report and release recommendation. | 12 | 0
A-013 | Pillar A – Returns | Self Assessment – Release 1 | Automation | Automation pack refresh | 2027-05-03 | 2027-05-28 | 2027-05-03 | 2027-05-28 | 0% | Not Started | Green | Test Manager | A-012 | Refresh of the regression automation pack. | 26 | 0
A-014 | Pillar A – Returns | Self Assessment – Release 1 | Holiday / Freeze | Christmas change freeze | 2026-12-21 | 2027-01-04 | 2026-12-21 | 2027-01-04 | 0% | Not Started | Green | Portfolio Test Lead |  | No change to test environments. | 15 | 0
A-015 | Pillar A – Returns | Self Assessment – Release 2 | Test Prep | Test design & scripting | 2026-06-22 | 2026-08-07 | 2026-06-22 | 2026-08-07 | 100% | Complete | Green | Test Manager |  | Design and peer-review of release test scenarios. | 47 | 0
A-016 | Pillar A – Returns | Self Assessment – Release 2 | Dependencies | Test environment & data readiness | 2026-07-20 | 2026-08-14 | 2026-07-20 | 2026-08-14 | 100% | Complete | Green | Portfolio Test Lead | A-015 | Environment build, masked test data load and access set-up. | 26 | 0
A-017 | Pillar A – Returns | Self Assessment – Release 2 | Smoke / P2P | Smoke & connectivity checks | 2026-08-10 | 2026-08-19 | 2026-08-10 | 2026-08-19 | 100% | Complete | Green | Test Manager | A-016 | Portal to API Gateway to Ledger connectivity smoke. | 10 | 0
A-018 | Pillar A – Returns | Self Assessment – Release 2 | SIT | SIT Cycle 1 execution | 2026-08-20 | 2026-11-06 | 2026-08-20 | 2026-10-27 | 56% | Delayed | Amber | Test Manager | A-017 | Functional system integration test, first cycle. | 79 | 10 | SAMPLE slip for demo
A-019 | Pillar A – Returns | Self Assessment – Release 2 | Defect Retest | Defect retest – Cycle 1 | 2026-10-19 | 2026-11-20 | 2026-10-19 | 2026-11-20 | 0% | Not Started | Green | Test Manager | A-018 | Retest of fixes delivered during Cycle 1. | 33 | 0
A-020 | Pillar A – Returns | Self Assessment – Release 2 | SIT | SIT Cycle 2 execution | 2026-11-23 | 2026-12-25 | 2026-11-23 | 2026-12-25 | 0% | Not Started | Green | Test Manager | A-019 | Second cycle incl. fix verification and new scope. | 33 | 0
A-021 | Pillar A – Returns | Self Assessment – Release 2 | Regression | Regression pack execution | 2027-01-18 | 2027-02-12 | 2027-01-18 | 2027-02-12 | 0% | Not Started | Green | Test Manager | A-020, A-028 | Full regression of in-scope journeys. | 26 | 0
A-022 | Pillar A – Returns | Self Assessment – Release 2 | TCR / Sign-off | SIT exit report & TCR | 2027-02-15 | 2027-02-26 | 2027-02-15 | 2027-02-26 | 0% | Not Started | Green | Portfolio Test Lead | A-021 | Test completion report and SIT sign-off. | 12 | 0
A-023 | Pillar A – Returns | Self Assessment – Release 2 | E2E | End-to-end journey testing | 2027-03-01 | 2027-04-02 | 2027-03-01 | 2027-04-02 | 0% | Not Started | Green | Test Manager | A-022 | Cross-system journeys across the portfolio. | 33 | 0
A-024 | Pillar A – Returns | Self Assessment – Release 2 | NFR | Performance & resilience testing | 2027-03-08 | 2027-04-09 | 2027-03-08 | 2027-04-09 | 0% | Not Started | Green | Test Manager | A-023 | Load, soak and failover tests on a production-like set-up. | 33 | 0
A-025 | Pillar A – Returns | Self Assessment – Release 2 | Defect Retest | Defect retest – E2E | 2027-04-05 | 2027-04-23 | 2027-04-05 | 2027-04-23 | 0% | Not Started | Green | Test Manager | A-024 | Retest of E2E and NFR defect fixes. | 19 | 0
A-026 | Pillar A – Returns | Self Assessment – Release 2 | TCR / Sign-off | E2E sign-off | 2027-04-26 | 2027-05-07 | 2027-04-26 | 2027-05-07 | 0% | Not Started | Green | Portfolio Test Lead | A-025 | E2E test completion report and release recommendation. | 12 | 0
A-027 | Pillar A – Returns | Self Assessment – Release 2 | Automation | Automation pack refresh | 2027-05-10 | 2027-06-04 | 2027-05-10 | 2027-06-04 | 0% | Not Started | Green | Test Manager | A-026 | Refresh of the regression automation pack. | 26 | 0
A-028 | Pillar A – Returns | Self Assessment – Release 2 | Holiday / Freeze | Christmas change freeze | 2026-12-21 | 2027-01-04 | 2026-12-21 | 2027-01-04 | 0% | Not Started | Green | Portfolio Test Lead |  | No change to test environments. | 15 | 0
B-001 | Pillar B – Payments | Self Assessment – Release 3 | Test Prep | Test design & scripting | 2026-06-29 | 2026-08-14 | 2026-06-29 | 2026-08-14 | 100% | Complete | Green | Test Manager |  | Design and peer-review of release test scenarios. | 47 | 0
B-002 | Pillar B – Payments | Self Assessment – Release 3 | Dependencies | Test environment & data readiness | 2026-07-27 | 2026-08-21 | 2026-07-27 | 2026-08-21 | 100% | Complete | Green | Portfolio Test Lead | B-001 | Environment build, masked test data load and access set-up. | 26 | 0
B-003 | Pillar B – Payments | Self Assessment – Release 3 | Smoke / P2P | Smoke & connectivity checks | 2026-08-17 | 2026-08-26 | 2026-08-17 | 2026-08-26 | 100% | Complete | Green | Test Manager | B-002 | Portal to API Gateway to Ledger connectivity smoke. | 10 | 0
B-004 | Pillar B – Payments | Self Assessment – Release 3 | SIT | SIT Cycle 1 execution | 2026-08-27 | 2026-11-13 | 2026-08-27 | 2026-11-13 | 47% | In Progress | Green | Test Manager | B-003 | Functional system integration test, first cycle. | 79 | 0
B-005 | Pillar B – Payments | Self Assessment – Release 3 | Defect Retest | Defect retest – Cycle 1 | 2026-10-26 | 2026-11-27 | 2026-10-26 | 2026-11-06 | 0% | Delayed | Red | Test Manager | B-004 | Retest of fixes delivered during Cycle 1. | 33 | 21 | SAMPLE slip for demo
B-006 | Pillar B – Payments | Self Assessment – Release 3 | SIT | SIT Cycle 2 execution | 2026-11-30 | 2027-01-01 | 2026-11-30 | 2027-01-01 | 0% | Not Started | Green | Test Manager | B-005 | Second cycle incl. fix verification and new scope. | 33 | 0
B-007 | Pillar B – Payments | Self Assessment – Release 3 | Regression | Regression pack execution | 2027-01-25 | 2027-02-19 | 2027-01-25 | 2027-02-19 | 0% | Not Started | Green | Test Manager | B-006, B-014 | Full regression of in-scope journeys. | 26 | 0
B-008 | Pillar B – Payments | Self Assessment – Release 3 | TCR / Sign-off | SIT exit report & TCR | 2027-02-22 | 2027-03-05 | 2027-02-22 | 2027-03-05 | 0% | Not Started | Green | Portfolio Test Lead | B-007 | Test completion report and SIT sign-off. | 12 | 0
B-009 | Pillar B – Payments | Self Assessment – Release 3 | E2E | End-to-end journey testing | 2027-03-08 | 2027-04-09 | 2027-03-08 | 2027-04-09 | 0% | Not Started | Green | Test Manager | B-008 | Cross-system journeys across the portfolio. | 33 | 0
B-010 | Pillar B – Payments | Self Assessment – Release 3 | NFR | Performance & resilience testing |  |  |  |  | 0% | Dates TBC | Green | Test Manager | B-009 | Load, soak and failover tests on a production-like set-up.
B-011 | Pillar B – Payments | Self Assessment – Release 3 | Defect Retest | Defect retest – E2E | 2027-04-12 | 2027-04-30 | 2027-04-12 | 2027-04-30 | 0% | Not Started | Green | Test Manager | B-010 | Retest of E2E and NFR defect fixes. | 19 | 0
B-012 | Pillar B – Payments | Self Assessment – Release 3 | TCR / Sign-off | E2E sign-off | 2027-05-03 | 2027-05-14 | 2027-05-03 | 2027-05-14 | 0% | Not Started | Green | Portfolio Test Lead | B-011 | E2E test completion report and release recommendation. | 12 | 0
B-013 | Pillar B – Payments | Self Assessment – Release 3 | Automation | Automation pack refresh | 2027-05-17 | 2027-06-11 | 2027-05-17 | 2027-06-11 | 0% | Not Started | Green | Test Manager | B-012 | Refresh of the regression automation pack. | 26 | 0
B-014 | Pillar B – Payments | Self Assessment – Release 3 | Holiday / Freeze | Christmas change freeze | 2026-12-21 | 2027-01-04 | 2026-12-21 | 2027-01-04 | 0% | Not Started | Green | Portfolio Test Lead |  | No change to test environments. | 15 | 0
B-015 | Pillar B – Payments | Self Assessment – Digital Filing | Test Prep | Test design & scripting | 2026-07-13 | 2026-08-28 | 2026-07-13 | 2026-08-28 | 100% | Complete | Green | Test Manager |  | Design and peer-review of release test scenarios. | 47 | 0
B-016 | Pillar B – Payments | Self Assessment – Digital Filing | Dependencies | Test environment & data readiness | 2026-08-10 | 2026-09-04 | 2026-08-10 | 2026-09-04 | 100% | Complete | Green | Portfolio Test Lead | B-015 | Environment build, masked test data load and access set-up. | 26 | 0
B-017 | Pillar B – Payments | Self Assessment – Digital Filing | Smoke / P2P | Smoke & connectivity checks | 2026-08-31 | 2026-09-09 | 2026-08-31 | 2026-09-09 | 100% | Complete | Green | Test Manager | B-016 | Portal to API Gateway to Ledger connectivity smoke. | 10 | 0
B-018 | Pillar B – Payments | Self Assessment – Digital Filing | SIT | SIT Cycle 1 execution | 2026-09-10 | 2026-11-27 | 2026-09-10 | 2026-11-27 | 29% | In Progress | Green | Test Manager | B-017 | Functional system integration test, first cycle. | 79 | 0
B-019 | Pillar B – Payments | Self Assessment – Digital Filing | Defect Retest | Defect retest – Cycle 1 | 2026-11-09 | 2026-12-11 | 2026-11-09 | 2026-12-11 | 0% | Not Started | Green | Test Manager | B-018 | Retest of fixes delivered during Cycle 1. | 33 | 0
B-020 | Pillar B – Payments | Self Assessment – Digital Filing | SIT | SIT Cycle 2 execution | 2026-12-14 | 2027-01-15 | 2026-12-14 | 2027-01-15 | 0% | Not Started | Green | Test Manager | B-019 | Second cycle incl. fix verification and new scope. | 33 | 0
B-021 | Pillar B – Payments | Self Assessment – Digital Filing | Regression | Regression pack execution | 2027-02-08 | 2027-03-05 | 2027-02-08 | 2027-03-05 | 0% | Not Started | Green | Test Manager | B-020, B-028 | Full regression of in-scope journeys. | 26 | 0
B-022 | Pillar B – Payments | Self Assessment – Digital Filing | TCR / Sign-off | SIT exit report & TCR | 2027-03-08 | 2027-03-19 | 2027-03-08 | 2027-03-19 | 0% | Not Started | Green | Portfolio Test Lead | B-021 | Test completion report and SIT sign-off. | 12 | 0
B-023 | Pillar B – Payments | Self Assessment – Digital Filing | E2E | End-to-end journey testing |  |  |  |  | 0% | Dates TBC | Green | Test Manager | B-022 | Cross-system journeys across the portfolio.
B-024 | Pillar B – Payments | Self Assessment – Digital Filing | NFR | Performance & resilience testing | 2027-03-29 | 2027-04-30 | 2027-03-29 | 2027-04-30 | 0% | Not Started | Green | Test Manager | B-023 | Load, soak and failover tests on a production-like set-up. | 33 | 0
B-025 | Pillar B – Payments | Self Assessment – Digital Filing | Defect Retest | Defect retest – E2E | 2027-04-26 | 2027-05-14 | 2027-04-26 | 2027-05-14 | 0% | Not Started | Green | Test Manager | B-024 | Retest of E2E and NFR defect fixes. | 19 | 0
B-026 | Pillar B – Payments | Self Assessment – Digital Filing | TCR / Sign-off | E2E sign-off | 2027-05-17 | 2027-05-28 | 2027-05-17 | 2027-05-28 | 0% | Not Started | Green | Portfolio Test Lead | B-025 | E2E test completion report and release recommendation. | 12 | 0
B-027 | Pillar B – Payments | Self Assessment – Digital Filing | Automation | Automation pack refresh | 2027-05-31 | 2027-06-25 | 2027-05-31 | 2027-06-25 | 0% | Not Started | Green | Test Manager | B-026 | Refresh of the regression automation pack. | 26 | 0
B-028 | Pillar B – Payments | Self Assessment – Digital Filing | Holiday / Freeze | Christmas change freeze | 2026-12-21 | 2027-01-04 | 2026-12-21 | 2027-01-04 | 0% | Not Started | Green | Portfolio Test Lead |  | No change to test environments. | 15 | 0

## POAP_Milestones
POAP - Milestones
Key dates drawn as diamonds on the roadmap and in the Plan on a Page milestone strip.
HOW TO FILL: one row per milestone. Pillar/Topic optional (blank = programme-wide).
ID | Pillar | Topic | Milestone | Date | Type | Status | Notes
M-01 | Pillar A – Returns | Self Assessment – Release 1 | Release 1 SIT start | 2026-08-13 | SIT Start | Achieved
M-02 | Pillar A – Returns | Self Assessment – Release 1 | Release 1 SIT Cycle 1 end | 2026-10-30 | SIT End | Planned
M-03 | Pillar A – Returns | Self Assessment – Release 2 | Release 2 SIT start | 2026-08-20 | SIT Start | Achieved
M-04 | Pillar A – Returns | Self Assessment – Release 2 | Release 2 SIT Cycle 1 end | 2026-11-06 | SIT End | At Risk | Slipping – see POAP_Plan
M-05 | Pillar B – Payments | Self Assessment – Release 3 | Release 3 SIT start | 2026-08-27 | SIT Start | Achieved
M-06 | Pillar B – Payments | Self Assessment – Release 3 | Release 3 SIT Cycle 1 end | 2026-11-13 | SIT End | Planned
M-07 | Pillar B – Payments | Self Assessment – Digital Filing | Digital Filing SIT start | 2026-09-10 | SIT Start | Achieved
M-08 | Pillar A – Returns | Self Assessment – Release 1 | Release 1 SIT exit sign-off | 2027-02-19 | Sign-off / TCR | Planned
M-09 |  |  | Test environment refresh complete | 2026-10-16 | Environment | Planned | Programme-wide
M-10 | Pillar B – Payments | Self Assessment – Release 3 | Vendor drop 3.2 delivered | 2026-10-09 | Dependency | At Risk | Awaiting vendor confirmation
M-11 |  |  | Christmas change freeze begins | 2026-12-21 | Gate | Planned | Programme-wide
M-12 | Pillar A – Returns | Self Assessment – Release 1 | Release 1 go-live gate | 2027-05-14 | Go-Live | Planned | Go / no-go decision

## P2P_Matrix
POAP - P2P Matrix (point-to-point integration flows)
One row per integration flow; four result chips (2xx/3xx/4xx/5xx) per flow.
SAMPLE – fictional data. HOW TO FILL: System Path uses ' → ' between systems (e.g. Portal → API Gateway → Ledger). Results from the dropdown.
Flow ID | Topic | Sub Process | System Path | Test No | Parent Test | Document | Planned Date | Status | 2xx (success) | 3xx (redirect) | 4xx (client error) | 5xx (server error) | Notes
F-01 | Self Assessment – Release 1 | Return submission | Portal → API Gateway → Ledger | Test 1 | P2P – Flow 01 | FLOW-SPEC-01 | 2026-08-07 | Complete | Pass | Pass | Pass | Pass
F-02 | Self Assessment – Release 1 | Payment on account | Ledger → Notification Service | Test 2 | P2P – Flow 02 | FLOW-SPEC-02 | 2026-08-12 | Complete | Pass | Pass | Pass | Pass
F-03 | Self Assessment – Release 2 | Amend a return | Portal → API Gateway → Document Store | Test 3 | P2P – Flow 03 | FLOW-SPEC-03 | 2026-09-18 | In Progress | Pass | Pass | Fail | Not Run | Defect raised for 4xx validation message
F-04 | Self Assessment – Release 2 | Supporting documents | API Gateway → Document Store | Test 4 | P2P – Flow 04 | FLOW-SPEC-04 | 2026-09-25 | In Progress | Pass | Not Run | Not Run | Not Run
F-05 | Self Assessment – Release 3 | Instalment plan set-up | Portal → API Gateway → Ledger → Notification Service | Test 5 | P2P – Flow 05 | FLOW-SPEC-05 | 2026-10-14 | Blocked | Blocked | Not Run | Not Run | Not Run | Blocked by test environment outage
F-06 | Self Assessment – Release 3 | Refund notification | Ledger → Notification Service | Test 6 | P2P – Flow 06 | FLOW-SPEC-06 | 2026-10-28 | Not Started | Not Run | Not Run | Not Run | Not Run
F-07 | Self Assessment – Digital Filing | Online filing hand-off | Portal → API Gateway | Test 7 | P2P – Flow 07 | FLOW-SPEC-07 | 2026-10-21 | Not Started | Not Run | N/A | Not Run | Not Run
F-08 | Self Assessment – Digital Filing | Receipt retrieval | Document Store → API Gateway → Portal | Test 8 | P2P – Flow 08 | FLOW-SPEC-08 |  | Dates TBC | Not Run | Not Run | Not Run | Not Run

## Lists
Pillar | Activity Type | Status | RAG | Milestone Type | Milestone Status | P2P Status | P2P Result
Pillar A – Returns | Test Prep | Not Started | Green | SIT Start | Planned | Not Started | Not Run
Pillar B – Payments | Dependencies | In Progress | Amber | SIT End | Achieved | In Progress | Pass
| Regression | Complete | Red | Sign-off / TCR | At Risk | Complete | Fail
| SIT | Delayed |  | Environment | Missed | Blocked | Blocked
| Smoke / P2P | On Hold |  | Dependency |  | Dates TBC | N/A
| Defect Retest | Dates TBC |  | Go-Live
| TCR / Sign-off |  |  | Gate
| E2E |  |  | Other
NFR
Automation
Holiday / Freeze
Other