## Summary Sheet
RAID Log – Summary
SAMPLE – fictional data for demonstration only.
Project Name | Self Assessment
TSR ID | TSR_SAMPLE-000001
Programme Test Manager | TBC
Start Date | 2026-07-01
End Date | 2027-06-30
Version | 1
Rating legend (likelihood x impact)
Rating | Score range
Very Low | 1 – 4
Low | 5 – 9
Medium | 10 – 14
High | 15 – 19
Very High | 20+

## Risks
Risk Register
One row per risk. Likelihood x Impact gives the score band used by the dashboard.
SAMPLE – fictional data for demonstration only. Yellow cells are inputs.
ID | Summary Title | Description | Category | Likelihood | Likelihood Rating | Previous Occurrence | Impact | Impact Rating | Risk Score | Status | Mitigation Details / Narrative | Owner | Review Date | Where Raised | Prog RAID | Prog RAID Reference | Archived
R-001 | Test environment instability delays SIT | Shared test environments suffer unplanned outages during peak execution weeks. | Environment | Likely | 1900-01-03 | Yes | Major | 1900-01-03 | High | Open | Daily environment health check; agree outage windows; escalate repeated outages to the platform lead. | Portfolio Test Lead | 2026-10-09 | Weekly test review | Yes | PR-0101 | No
R-002 | Test data not representative or delivered late | Masked data sets arrive after cycle start, limiting scenario coverage. | Test Data | Possible | 1900-01-02 | Yes | Major | 1900-01-03 | Medium | Open | Raise data requests two sprints ahead; keep a minimum reusable data baseline. | Test Manager | 2026-10-16 | Planning workshop | No |  | No
R-003 | Vendor drop delivered late | Vendor build for the next release is not delivered by the agreed date, compressing SIT. | Supplier | Very Likely | 1900-01-04 | Yes | Major | 1900-01-03 | Very High | Open | Weekly vendor checkpoint; agree entry criteria; re-plan SIT window if drop slips beyond 5 days. | Programme Test Manager | 2026-10-09 | Steering group | Yes | PR-0102 | No
R-004 | Loss of key test analyst | Single points of knowledge for integration scenarios; attrition would slow execution. | Resourcing | Possible | 1900-01-02 | No | Moderate | 1900-01-02 | Low | Open | Pair working and documented scenario ownership; identify backup analysts. | Test Manager | 2026-10-23 | Resourcing review | No |  | No
R-005 | Late requirements change | Scope changes after test design baseline force rework of scripts and data. | Requirements | Likely | 1900-01-03 | Yes | Moderate | 1900-01-02 | Medium | Open | Change control with test impact assessment; freeze scope two weeks before cycle start. | Portfolio Test Lead | 2026-10-16 | Change board | No |  | No
R-006 | Regression scope growth | Each release adds journeys to the regression pack faster than capacity grows. | Scope | Likely | 1900-01-03 | No | Major | 1900-01-03 | High | Open | Risk-based regression selection; invest in automation for stable journeys. | Test Manager | 2026-10-30 | Planning workshop | No |  | No
R-007 | Defect fix turnaround exceeds target | Fix turnaround above five working days delays retest and sign-off. | Defects | Likely | 1900-01-03 | Yes | Moderate | 1900-01-02 | Medium | Mitigated | Daily defect triage with delivery leads; fast-track severity 1 and 2 items. | Test Manager | 2026-10-09 | Defect triage | No |  | No
R-008 | Third-party sandbox unavailable | External sandbox used for notification testing has limited availability. | Environment | Low | 1900-01-01 | No | Major | 1900-01-03 | Low | Open | Stub fallback agreed; book sandbox slots in advance. | Portfolio Test Lead | 2026-11-06 | Weekly test review | No |  | No
R-009 | Automation framework maintenance backlog | Framework upgrades are deferred, increasing script flakiness. | Automation | Low | 1900-01-01 | No | Minor | 1900-01-01 | Very Low | Open | Allocate fixed weekly maintenance time. | Test Manager | 2026-11-13 | Retrospective | No |  | No
R-010 | Christmas freeze compresses test window | The change freeze removes two weeks of execution capacity. | Planning | Possible | 1900-01-02 | No | Moderate | 1900-01-02 | Low | Closed | Plan agreed: Cycle 2 completes before the freeze; regression starts after. | Portfolio Test Lead | 2026-09-18 | Planning workshop | No |  | No
R-011 | Performance environment not production-like | NFR results may not be representative if sizing differs from production. | Environment | Possible | 1900-01-02 | Yes | Major | 1900-01-03 | Medium | Mitigated | Sizing comparison documented; results caveated and extrapolated by the platform team. | Test Manager | 2026-10-23 | NFR working group | Yes | PR-0103 | No
R-012 | New joiner access delays | Account and tooling access takes more than a week for new starters. | Resourcing | Low | 1900-01-01 | Yes | Minor | 1900-01-01 | Very Low | Closed | Access pre-requested during onboarding. | Test Manager | 2026-09-04 | Resourcing review | No |  | No
R-013 | Unclear ownership of E2E scenarios | Cross-team journeys lack a named scenario owner, risking gaps. | Governance | Possible | 1900-01-02 | No | Minor | 1900-01-01 | Low | Open | Agree scenario ownership matrix at the next test forum. | Portfolio Test Lead | 2026-10-30 | Test forum | No |  | No
R-014 | Test tooling licence expiry | Licences for the test management tool expire during the programme. | Tooling | Very Low | 1899-12-31 | No | Moderate | 1900-01-02 | Very Low | Closed | Renewal confirmed to end of programme. | Programme Test Manager | 2026-09-11 | Weekly test review | No |  | No

## Issues
Issue Log
One row per issue. Priority x Severity gives the overall rating.
SAMPLE – fictional data for demonstration only. Yellow cells are inputs.
ID | Summary Title | Full Description | Tracking ID Reference (Link) | Reporter | Owner | Date Reported | Priority | Priority Rating | Severity | Severity Rating | Overall Issue Rating | Status | Original Risk ID | Target Resolution Date | Actual Resolution Date | Resolution Summary | Notes/Actions | Where Raised | Prog RAID | Prog RAID Reference | Archived
I-001 | Test environment outage blocks SIT execution | Unplanned outage of the shared integration environment has halted SIT execution for several days. | TRK-2001 | Test Manager | Portfolio Test Lead | 2026-09-28 | Very High | 5 | Severe | 5 | Very High | Open | R-001 | 2026-10-09 |  |  | Environment team investigating; daily call in place. | Weekly test review | Yes | PR-0201 | No
I-002 | Defect fix backlog above target | Open defects awaiting fix have exceeded the agreed turnaround target. | TRK-2002 | Test Manager | Portfolio Test Lead | 2026-09-14 | High | 4 | Major | 4 | High | Resolution in progress | R-007 | 2026-10-16 |  |  | Extra delivery capacity agreed; backlog reducing weekly. | Defect triage | No |  | No
I-003 | Test data load failure in Cycle 1 | Masked data load failed validation and had to be re-run. | TRK-2003 | Test Manager | Test Manager | 2026-09-07 | Medium | 3 | Moderate | 3 | Low | Resolved | R-002 | 2026-09-18 | 2026-09-16 | Data load corrected and re-run successfully. | Closed after re-run. | Weekly test review | No |  | No
I-004 | Interface contract mismatch between Portal and API Gateway | Field length mismatch caused submission failures in SIT. | TRK-2004 | Test Manager | Portfolio Test Lead | 2026-09-10 | High | 4 | Moderate | 3 | Medium | Resolved |  | 2026-09-25 | 2026-09-23 | Contract aligned and fix deployed. | Regression test added. | Defect triage | No |  | No
I-005 | Notification Service sandbox intermittent | Sandbox responses are intermittent, producing false failures. | TRK-2005 | Test Manager | Portfolio Test Lead | 2026-09-21 | Medium | 3 | Moderate | 3 | Low | Resolution in progress | R-008 | 2026-10-23 |  |  | Stub fallback in use while the sandbox is stabilised. | Weekly test review | No |  | No

## Assumptions
Assumptions Log
One row per assumption with a validation action and due date.
SAMPLE – fictional data for demonstration only. Yellow cells are inputs.
ID | Description | Raised By | Date Logged | Confidence Level | Impact if Assumption is Incorrect | Validation Action / Narrative | Validation Due Date | Status | Notes/Actions | Where Raised | Prog RAID | Prog RAID Reference | Archived
A-001 | Production-like test data will be available before each SIT cycle starts. | Test Manager | 2026-07-06 | Medium | Reduced coverage and delayed execution. | Confirm data refresh schedule with the data team. | 2026-10-16 | Unconfirmed |  | Planning workshop | No |  | No
A-002 | The vendor will deliver builds on the agreed fortnightly cadence. | Programme Test Manager | 2026-07-06 | Low | SIT window compressed; sign-off dates at risk. | Weekly vendor checkpoint. | 2026-10-09 | Unconfirmed |  | Steering group | Yes | PR-0301 | No
A-003 | Test environments are available 24x7 except for agreed maintenance windows. | Portfolio Test Lead | 2026-07-13 | High | Execution blocked; schedule impact. | Review environment availability report monthly. | 2026-11-06 | Confirmed Correct | Availability report reviewed. | Planning workshop | No |  | No
A-004 | Regression pack scope is limited to in-scope journeys agreed at baseline. | Test Manager | 2026-09-04 | Medium | Additional regression effort required. | Confirm scope with the product owner. | 2026-10-30 | Unconfirmed |  | Weekly test review | No |  | No
A-005 | No change to non-functional requirements after baseline. | Test Manager | 2026-09-14 | High | NFR re-planning and rework. | Sign-off of NFR catalogue. | 2026-09-25 | Confirmed Correct | NFR catalogue signed off. | NFR working group | No |  | No
A-006 | Existing automation covers at least 60% of regression journeys. | Test Manager | 2026-09-21 | Medium | Manual regression effort increases. | Automation coverage review. | 2026-11-13 | Unconfirmed |  | Retrospective | No |  | No

## Dependencies
Dependency Log
One row per dependency; the dashboard lists open items due in the next 30 days.
SAMPLE – fictional data for demonstration only. Yellow cells are inputs.
ID | Description | Dependency For (Who Needs This) | Dependency From (Who Delivers This) | Type | Date Required | Requestor | Owner | Priority | Impact If Not Met | Status | Notes/Actions | Where Raised | Prog RAID | Prog RAID Reference | Archived
D-001 | Vendor build 3.2 for Release 3 SIT entry | SIT team | Vendor delivery team | Delivery | 2026-10-09 | Test Manager | Programme Test Manager | Very High | SIT start delayed by the same duration. | Open | Checkpoint twice weekly. | Steering group | Yes | PR-0401 | No
D-002 | Refreshed test environment for Release 2 | SIT team | Environment team | Environment | 2026-10-16 | Test Manager | Portfolio Test Lead | High | Cycle 1 completion slips. | Open | Refresh scheduled for the weekend. | Weekly test review | No |  | No
D-003 | Masked data set for Digital Filing | Test design | Data team | Data | 2026-10-23 | Test Manager | Test Manager | High | Scenarios cannot be executed. | Open |  | Planning workshop | No |  | No
D-004 | Notification Service sandbox slots for Release 3 | Smoke / P2P | Third-party integration team | Third Party | 2026-10-28 | Test Manager | Portfolio Test Lead | Medium | Fallback to stubs reduces confidence. | Open | Slots to be booked. | Weekly test review | No |  | No
D-005 | Approved NFR catalogue | NFR testing | Architecture | Requirements | 2026-11-20 | Portfolio Test Lead | Portfolio Test Lead | Medium | NFR test design delayed. | Open |  | NFR working group | No |  | No
D-006 | Two additional test analysts onboarded | Test execution | Resourcing | Resource | 2026-12-04 | Test Manager | Programme Test Manager | High | Execution capacity shortfall in Cycle 2. | Open |  | Resourcing review | No |  | No
D-007 | Test management tool upgrade | All test teams | Tooling team | Tooling | 2026-09-18 | Test Manager | Portfolio Test Lead | Medium | Reporting gaps. | Closed | Upgrade completed. | Weekly test review | No |  | No
D-008 | Interface contract baseline for Portal and API Gateway | Test design | Solution design | Requirements | 2026-08-14 | Test Manager | Portfolio Test Lead | Very High | Test design cannot be baselined. | Closed | Contract baselined. | Planning workshop | No |  | No

## User Guide
RAID Log – User Guide
SAMPLE – fictional data for demonstration only.
Summary Sheet | Project details in column E (Project Name, TSR ID, Programme Test Manager, Start Date, End Date, Version) and the rating legend.
Risks / Issues / Assumptions / Dependencies | Header row is row 10, data from row 11, ID in column C. Keep header text exactly as written - the dashboard finds columns by name.
Ratings | Risk score = Likelihood rating x Impact rating: <5 Very Low, <10 Low, <15 Medium, <20 High, otherwise Very High. Issues use Priority x Severity.
Status | Risks: Open / Mitigated / Closed. Issues: Open / Resolution in progress / Resolved / Closed. Dependencies: Open / Closed. Archived = Yes hides a row from the dashboard.
Colours | Yellow cells with blue text are inputs. Use the dropdowns where provided.