## Guide
ATS Plan on a Page (POAP) workbook
Fill this workbook once, drop it into the ATS Dashboard (POAP section) and it renders a filterable roadmap, an executive Plan-on-a-Page and the integration-flow matrix.
HOW TO USE
1. POAP_Config | Set program name, plan start/end and (optionally) a status date. Leave the status date blank to use today's date. Set Data Mode to LIVE for real data (SAMPLE shows a ribbon in the dashboard). Edit pillar/activity colours if you like (hex, no #).
2. POAP_Plan | One row per BAR on the roadmap. Pillar > Topic is the swimlane; Activity Type picks the colour and the phase on the Plan on a Page. Start/End are real dates. Baseline = the originally agreed dates (the dashboard draws a ghost bar and a +Nd slip badge when End moves past Baseline End). % Complete is 0-100% (0-1 also accepted).
Depends On: comma-separated IDs from column A (e.g. P1-004, P1-007) - the dashboard draws dependency arrows. Status 'Dates TBC': leave Start/End blank (or give an indicative date) and the bar shows hatched / in the TBC strip. Duration and Slip are calculated (grey) - do not type in them.
3. POAP_Milestones | Key dates shown as diamonds on the roadmap lane and in the Plan on a Page milestone strip.
4. P2P_Matrix | Point-to-point integration flows. System Path uses ' → ' between systems (also accepts -> or >). Record the result of each response class (2xx/3xx/4xx/5xx) from the dropdowns.
5. Lists | Dropdown values. Add values at the bottom of a list only if you also extend the matching colour table in POAP_Config.
COLOURS
Yellow cells / blue text | Inputs you type or paste.
Grey cells | Calculated - leave alone.
Grey italic row | EXAMPLE rows (Notes start with 'EXAMPLE') are ignored by the dashboard - overwrite or delete them.
STATUS RULES OF THUMB
Complete | End date in the past or work signed off; set % Complete to 100%.
Delayed | End has moved later than Baseline End; set RAG Amber/Red and explain in Notes.
Dates TBC | Dates not yet agreed; shown dashed/hatched and listed in the 'At risk / slipping' panel.

## POAP_Config
POAP Configuration
Global settings, pillar colours and activity-type colours used by the dashboard.
HOW TO FILL: edit the yellow cells only. Colours are hex without the # sign.
Setting | Value | Description
Program Name | <Programme> – <Portfolio Name> test delivery | Shown in the top strip of the POAP section.
Plan Start Date |  | Left edge of the roadmap (blank = earliest bar).
Plan End Date |  | Right edge of the roadmap (blank = latest bar).
Status Date (blank = today) |  | 'As at' date used for the today line, KPIs and Next 30 days.
Data Mode | LIVE | SAMPLE shows a ribbon in the dashboard; use LIVE for real data.
PILLARS
Pillar | Colour (hex, no #)
Pillar 1 | 2563EB
Pillar 2 | 0EA5A0
Pillar 3 | 8B5CF6
Penalties P2P (WBS) | EC4899
Cross-cutting | 64748B
ACTIVITY TYPES
Activity Type | Colour (hex, no #)
Test Prep | 8B9DF8
Dependencies | C2A878
Regression | 0EA5E9
SIT | 3B5BDB
Smoke / P2P | 06B6D4
Defect Retest | E86AA6
TCR / Sign-off | 0F766E
E2E | 7C3AED
NFR | C084FC
Automation | 475569
Holiday / Freeze | CBD5E1
Other | 94A3B8

## POAP_Plan
POAP - Plan (one row per roadmap bar)
Each row is a bar on the roadmap: Pillar > Topic swimlane, coloured by Activity Type.
HOW TO FILL: yellow = input, grey = calculated. Dates as yyyy-mm-dd. Depends On = comma-separated IDs. Baseline = originally agreed dates (drives the slip badge).
IDENTITY |  |  |  |  | CURRENT DATES |  | BASELINE |  | PROGRESS & LINKS |  |  |  |  | SCOPE | CALCULATED |  | ADMIN
ID | Pillar | Topic | Activity Type | Item | Start | End | Baseline Start | Baseline End | % Complete | Status | RAG | Owner | Depends On | Scope / Notes | Duration (Days) | Slip (Days) | Notes
EX-001 | Pillar 1 | Repayments | SIT | SIT Execution - Cycle 1 | 2026-07-20 | 2026-11-06 | 2026-07-20 | 2026-10-23 | 60% | In Progress | Amber | Test Lead |  | Example scope text | 110 | 14 | EXAMPLE – delete this row

## POAP_Milestones
POAP - Milestones
Key dates drawn as diamonds on the roadmap and in the Plan on a Page milestone strip.
HOW TO FILL: one row per milestone. Pillar/Topic optional (blank = programme-wide).
ID | Pillar | Topic | Milestone | Date | Type | Status | Notes
EX-M01 | Pillar 1 | Repayments | SIT Cycle 1 exit sign-off | 2026-12-04 | Sign-off / TCR | Planned | EXAMPLE – delete this row

## P2P_Matrix
POAP - P2P Matrix (point-to-point integration flows)
One row per integration flow; four result chips (2xx/3xx/4xx/5xx) per flow.
HOW TO FILL: System Path uses ' → ' between systems (e.g. System A → System B → System C). Results from the dropdown.
Flow ID | Topic | Sub Process | System Path | Test No | Parent Test | Document | Planned Date | Status | 2xx (success) | 3xx (redirect) | 4xx (client error) | 5xx (server error) | Notes
EX-F01 | Penalties | Late Filing Penalties | System C → System B → System A | Test 1 | P2P - API-1 | API-1 | 2026-06-16 | Complete | Pass | Pass | Pass | Pass | EXAMPLE – delete this row

## Lists
Pillar | Activity Type | Status | RAG | Milestone Type | Milestone Status | P2P Status | P2P Result
Pillar 1 | Test Prep | Not Started | Green | SIT Start | Planned | Not Started | Not Run
Pillar 2 | Dependencies | In Progress | Amber | SIT End | Achieved | In Progress | Pass
Pillar 3 | Regression | Complete | Red | Sign-off / TCR | At Risk | Complete | Fail
Penalties P2P (WBS) | SIT | Delayed |  | Environment | Missed | Blocked | Blocked
Cross-cutting | Smoke / P2P | On Hold |  | Dependency |  | Dates TBC | N/A
| Defect Retest | Dates TBC |  | Go-Live
| TCR / Sign-off |  |  | Gate
| E2E |  |  | Other
NFR
Automation
Holiday / Freeze
Other