## Instructions
ATS Portfolio Data Template — Instructions
What is this file? | One workbook = one Portfolio's data for one reporting month. Save one copy per portfolio per month.
Sheet: KPI_Summary | Fill in the yellow cells only (Portfolio Name, Month, Actuals for each of the 8 KPI metrics). RAG Status and variance are calculated automatically — do not overwrite those formulas.
Sheet: TSR | One row per Test Scope Request (TSR) received. Fill in the yellow columns only. SLA Due Date, Response Status and Breach Flag are calculated automatically from the dates you enter — do not type over those columns.
SLA rule | TSRs must receive a response within 5 calendar days of receipt. If Date Responded is blank, the TSR is treated as Pending. If it is filled in after the SLA Due Date, it is flagged SLA Overdue (a contractual breach).
File naming | Name the file exactly as the Portfolio Name, e.g. 'Self Assessment.xlsx'. Do not include the month in the filename — the month lives inside the workbook and the folder it's placed in.
Folder structure the dashboard expects | ATS_Data / <YYYY-MM> / <Portfolio Name>.xlsx — e.g. ATS_Data/2026-09/Self Assessment.xlsx
Yellow cells | Please fill these in.
White cells with blue text | Automatically calculated. Leave untouched.
Legend
Fill this in
Auto-calculated — do not edit

## KPI_Summary
ATS Portfolio — KPI Summary
Portfolio Name | Child Benefit |  | Reporting Month (YYYY-MM) | 2026-09
Prepared By |  |  | Date Prepared | 2026-09-28
# | Metric | Unit | Direction | Target | Actual | RAG Status | Comments
1 | Defect Leakage | % | Lower | 5 | 7.1 | Red
2 | Level of Automated Testing | % | Higher | 70 | 64.9 | Amber
3 | Customer Satisfaction | % | Higher | 90 | 87.9 | Amber
4 | Risk-Based Test Coverage | % | Higher | 95 | 89.5 | Amber
5 | Defect Detection Rate | % | Higher | 92 | 87.9 | Amber
6 | Test Execution Downtime | hrs | Lower | 8 | 11.1 | Red
7 | Defect Turnaround Time | days | Lower | 3 | 4.6 | Red
8 | Critical Test Milestone Delays | count | Lower | 0 | 1 | Red

## TSR
ATS Portfolio — TSR Log (Test Scope Requests)
SLA = 5 calendar days from Date Received. Response Status, SLA Due Date and Breach Flag are calculated automatically.
# | TSR ID | Scope Description | Date Received | SLA Due Date | Date Responded | Resource Count | Response Status | Pending Sub-Status | Breach (Fine Applicable) | Comments
1 | TSR-202609-001 | Security test scope addition | 2026-09-04 | 2026-09-09 | 2026-09-08 | 1 | SLA Met |  | No
2 | TSR-202609-002 | New scope testing for release increment | 2026-09-10 | 2026-09-15 | 2026-09-13 | 10 | SLA Met |  | No
3 | TSR-202609-003 | Resource ramp-up for regression cycle | 2026-09-17 | 2026-09-22 | 2026-09-26 | 2 | SLA Overdue |  | Yes
4 | TSR-202609-004 | New scope testing for release increment | 2026-09-12 | 2026-09-17 | 2026-09-15 | 5 | SLA Met |  | No
5 | TSR-202609-005 | Performance test scope for peak load | 2026-09-19 | 2026-09-24 | 2026-09-28 | 10 | SLA Overdue |  | Yes
6 | TSR-202609-006 | New scope testing for release increment | 2026-09-20 | 2026-09-25 | 2026-09-25 | 10 | SLA Met |  | No
7 | TSR-202609-007 | New scope testing for release increment | 2026-09-22 | 2026-09-27 | 2026-09-25 | 3 | SLA Met |  | No
8 | TSR-202609-008 | Change request impact assessment | 2026-09-09 | 2026-09-14 | 2026-09-12 | 6 | SLA Met |  | No
9 | TSR-202609-009 | Performance test scope for peak load | 2026-09-01 | 2026-09-06 | 2026-09-08 | 11 | SLA Overdue |  | Yes
10 | TSR-202609-010 | New scope testing for release increment | 2026-09-13 | 2026-09-18 |  | 2 | Pending | Query Raised | No
11 | TSR-202609-011 | Additional environment test coverage | 2026-09-24 | 2026-09-29 | 2026-09-28 | 8 | SLA Met |  | No
12 | TSR-202609-012 | Change request impact assessment | 2026-09-11 | 2026-09-16 |  | 10 | Pending | Impacting | No
13 | TSR-202609-013 | Resource ramp-up for regression cycle | 2026-09-20 | 2026-09-25 |  | 10 | Pending | Impacting | No
14 | TSR-202609-014 | Additional environment test coverage | 2026-09-02 | 2026-09-07 | 2026-09-05 | 11 | SLA Met |  | No
15 | TSR-202609-015 | Additional environment test coverage | 2026-09-14 | 2026-09-19 | 2026-09-18 | 5 | SLA Met |  | No
16 | TSR-202609-016 | Change request impact assessment | 2026-09-07 | 2026-09-12 | 2026-09-08 | 7 | SLA Met |  | No
17 | TSR-202609-017 | Additional environment test coverage | 2026-09-04 | 2026-09-09 | 2026-09-09 | 9 | SLA Met |  | No
18 | TSR-202609-018 | Additional environment test coverage | 2026-09-22 | 2026-09-27 | 2026-09-24 | 10 | SLA Met |  | No
19 | TSR-202609-019 | Resource ramp-up for regression cycle | 2026-09-02 | 2026-09-07 |  | 3 | Pending | Impacting | No
20 | TSR-202609-020 | New scope testing for release increment | 2026-09-25 | 2026-09-30 | 2026-10-03 | 1 | SLA Overdue |  | Yes
Formulas:
SLA Due Date = IF([Date Received]="","",[Date Received]+5)