## Guide
ATS Weekly Data – User Guide
One workbook, filled once a week, feeds BOTH the Weekly Report and the Monthly Council dashboard.
BLANK TEMPLATE – Data Mode = LIVE. Each data sheet holds one grey italic EXAMPLE row: delete it when you add your first real row (rows whose Notes start with EXAMPLE are ignored by the dashboard anyway).
1. The idea: fill once, weekly
• Every Friday you add ONE new row to Weekly_Snapshot and one row per active topic to Topic_Progress and Readiness; defects, TSRs and milestones are updated whenever they change. Nothing is ever overwritten: history is kept as dated rows.
• A WEEK is a slice (the latest Week Ending). A MONTH or QUARTER is a roll-up of the weeks in it (see section 4). That is how the same file feeds the Weekly Report and the Monthly Council.
• Yellow cells (blue text) are for you to type or pick from a dropdown. Grey cells are formulas – never type over them. Dates are real dates shown as yyyy-mm-dd; use Alt+Enter for a new line inside a text cell.
• Do not rename sheets, rename or reorder column headers, or insert columns: the dashboard finds columns by header text. Adding new rows below the last row is always safe (about 300 rows are pre-formatted on each data sheet).
2. What to update and when
When | Sheet | What to do | Rows
Weekly (every Friday) | Weekly_Snapshot | Add 1 new row for the new Week Ending (a Friday). Enter cumulative-to-date counts, test days, downtime hours, FTE, spend and the Overall RAG + summary. | 1 per week
Weekly | Topic_Progress | 1 row per active topic: phase, test cases planned / designed, and cumulative passed, failed, blocked. | 1 per topic per week
Weekly | Defect_Log | Add new defects; update Status, Resolved Date, TCs Blocked and Triage Comments on existing ones. | As needed
Weekly | Readiness | 1 row per topic: planned SIT start, overall RAG, six readiness areas (RAG + note) and Road to Green. | 1 per topic per week
Weekly (optional) | Commentary | Narrative per KPI for the week: highlights, concern, actions, executive commentary; optional RAG / current-position override. | 0–16 per week
As they happen | TSR_Log | Add a TSR when received; fill Returned Date when sent back and Hold Days for time pending clarification. | 1 per TSR
As they happen | Milestones | Add each milestone once. Set Forecast Date if it slips and Completed Date when done. | 1 per milestone
As they happen | Defect_Log | Raise a defect the day it is logged; set Resolved Date when fix + confirmation test is complete (or on rejection). | 1 per defect
Monthly / Quarterly | Weekly_Snapshot (CSAT columns) | Enter the CSAT score and number of responses only in the week a survey result is received; otherwise leave blank (= 'Not Requested'). | Occasional
Monthly / Quarterly | Demand_Forecast | Refresh planned vs available FTE for the coming months. | 1 per month
Monthly / Quarterly | Lessons_Learned | Record lessons and improvement actions; update Status when actioned. | As needed
Monthly / Quarterly | Resourcing | Update when people join, change allocation or leave. | As needed
Yearly / rarely | Bank_Holidays, Config, Lists | Extend bank holidays each year; change RAG thresholds or add dropdown values (Lists) only when the rules change. | Rare
3. Colour legend
Sample | Input cell (yellow, blue) | Type here or pick from the dropdown.
Sample | Calculated cell (grey) | Formula – never type over it.
Sample | EXAMPLE row (grey italic) | Delete it; the dashboard ignores rows whose Notes start with EXAMPLE.
Green | Green | On track / within target.
Amber | Amber | At risk / watch closely.
Red | Red | Off track / action needed.
4. Flow vs cumulative: how weeks roll up into a month or quarter
Type | Measures | Roll-up rule | Why
FLOW measures | Planned Test Days, Downtime Hours | SUM over the weeks in the period. | Each week records only what happened that week.
CUMULATIVE / snapshot measures | Coverage, automation, test execution (passed / failed / blocked, designed), resources, cumulative spend, forecast at completion | Take the LATEST week in the period. | Each week records the running total to date, so the last week already contains everything before it.
Example: September availability = 1 − (sum of September downtime hours) ÷ (sum of September planned test days × hours per test day). Coverage for September = the value in the last September week.
5. RAG rules the dashboard applies (thresholds live on the Config sheet)
KPI | Rule |  | Source
Risk Based Coverage | Per risk level: coverage = Covered ÷ Requirements; Green ≥ target, Amber ≥ target − tolerance, else Red. Overall = worst of High and Medium. |  | ATS KPI Data Collation – M.Coverage (3.9)
Production Defect Leakage (quarterly) | Defects with Found In = Production in the quarter to date. Red if P1 ≥ 1 or P2 ≥ 5 or P3 ≥ 6; Amber if P2 in 1–4 or P3 in 1–5; else Green. 'Not in Production' while Go-Live is blank. |  | Q.Defects (3.1)
Defect Detection Effectiveness | DDE = Testing-found ÷ (Testing-found + Production-found). Also raised / rejected by priority; rejection % Green ≤ 5%, Amber ≤ 10%, else Red. |  | M.Defects (3.2)
Defect Aging | Working-day aging buckets; SLA compliance = share resolved within SLA days; Green ≥ 80%, Amber ≥ 60%, else Red. |  | M.Defect Turnaround (4.11); thresholds are an ASSUMPTION
Automation Coverage (quarterly) | Green if ≥ target (95%) or improved vs the previous period, else Amber. |  | Q.Automation (4.5)
Milestone Delivery | Per milestone: completed on time = Green, completed late = Red; open and past due = Red; due within 5 days = Amber; else Green. Overall Red if any Red; Amber if share of Amber > 20%; else Green. |  | M.Test Milestone Delays (4.15)
Environment Availability | Downtime hours: monthly Green ≤ 24, Amber ≤ 48, else Red; weekly thresholds are set on Config. |  | M.Downtime (4.14); weekly thresholds are an ASSUMPTION
TSR Impact Assessment | Red if any TSR working days > SLA (10), else Green. |  | M.TSR Assessment (3.5)
Customer Satisfaction (quarterly) | Green if score ≥ pass mark and not declining; Red if < pass mark and not improving; else Amber. 'Not Requested' if blank. |  | Q.Satisfaction (3.3)
Resource Position | Actual ÷ Planned: Green ≥ 100%, Amber ≥ 90%, else Red. |  | ASSUMPTION
Demand Forecast | Planned FTE vs Available FTE for the next 3 months: Green if available ≥ planned; Amber if gap ≤ 1 FTE; else Red. |  | ASSUMPTION
Commercial Performance | Forecast vs Budget: Green ≤ budget; Amber ≤ budget + 5%; else Red. |  | ASSUMPTION
RAID Health | Red if any open risk/issue is rated Very High (score ≥ 20); Amber if any High (15–19); else Green. |  | ASSUMPTION (from the Test RAID Log)
Test Execution Progress | Blocked ÷ planned TCs: Green ≤ 5%, Amber ≤ 20%, else Red. |  | ASSUMPTION
SIT Readiness | Worst latest overall RAG across topics in Readiness (from your weekly rows). |  | Derived from the Readiness sheet
6. The EXAMPLE-row rule
• Every data sheet (except Bank_Holidays and Lists) has a Notes column as its LAST column. Rows whose Notes start with the word EXAMPLE are ignored by the dashboard.
• The blank template ships with one grey italic EXAMPLE row on each data sheet (Notes = “EXAMPLE – delete this row”). Overwrite or delete it when you add your first real row. If you forget, nothing breaks – it is simply skipped.
• The demo workbooks in samples/ have no example rows: their rows are made-up illustrative history.
7. How to load into the dashboard
• Save this file as ATS_Weekly_Data.xlsx (see section 8 for the portfolio folder layout). Keep the RAID log in its own file (copy templates/ATS_RAID_Log_Template.xlsx as ATS_RAID_Log.xlsx: Risks, Issues, Assumptions, Dependencies, Decisions) and the plan in ATS_POAP.xlsx.
• Put all three files in the SAME folder.
• Open the dashboard and choose that folder in the load step; it reads the three workbooks offline and builds the Weekly Report and Monthly Council views.
• Weekly routine: open the file on Friday, add your rows, save, then click Refresh data in the dashboard.
8. Many portfolios, one design
• This workbook design is the same for EVERY portfolio. Each portfolio keeps its OWN copy: copy the template, set Portfolio Name (and Programme) on the Config sheet, then fill it weekly. Portfolio Name must be unique across portfolios.
• Recommended folder layout: ATS_Program/<Portfolio Name>/ATS_Weekly_Data.xlsx, with that portfolio's ATS_POAP.xlsx and RAID log in the same subfolder.
• Alternative: one flat folder with files named ATS_Weekly_Data - <Portfolio Name>.xlsx.
• In the dashboard: use Load program folder once and a portfolio dropdown appears. The Programme Overview compares all portfolios; Monthly Council, Weekly Report and POAP show the selected portfolio.
• A portfolio without a POAP or RAID file simply does not show those pages.

## Config
Config – programme details, thresholds and rules
Keys in column A are read by the dashboard (text must not change); edit only the yellow values in column B.
LIVE – blank template. Data Mode = LIVE.
Setting | Value | Description / assumption
Program Name | <Programme> – <Portfolio Name> | Shown in dashboard headers. Source: title slide of ATS – Monthly Council deck.
Project / Phase | <Project / phase> | Source: Commercials slide of the Monthly Council deck (Project = <Project / phase>).
TSR Reference | <TSR reference> | The programme's own TSR (QA activities and resource estimation). Source: Monthly Council deck (TSR Impact slide).
Programme Test Manager | <Name> | Source: Monthly Council deck, Resourcing slide.
Test Manager | <Name> | Source: Monthly Council deck, Resourcing slide.
Programme Start Date |  | Source: Monthly Council deck, Commercials slide (Start Date 01-07-2026).
Programme End Date |  | Programme end date as supplied by the test-delivery lead.
Total Budget (£) |  | Total cost on the Commercials slide of the Monthly Council deck.
Production Go-Live Date |  | Leave BLANK until the solution is live in production. Blank = 'Not in Production' (Production Defect Leakage is not scored).
Data Mode | LIVE | Leave as LIVE for real data. (SAMPLE is only used by the demo workbooks; the dashboard shows no badge either way.)
Hours per Test Day | 8 | Source: ATS KPI Data Collation – M.Downtime (4.14): Required Hours = test days x 8.
TSR SLA – Max Working Days | 10 | Source: ATS KPI Data Collation – M.TSR Assessment (3.5): Red if any TSR working days > 10.
Defect Turnaround SLA – Working Days | 5 | Source: M.Defect Turnaround (4.11) ageing buckets (0-2, 3-5, 6-10, >10 days). ASSUMPTION: not defined in the source KPI workbook; 5 working days is used as the SLA.
Defect Turnaround – Green if SLA compliance >= | 80% | ASSUMPTION – not defined in the source KPI workbook; turnaround RAG thresholds (share of defects resolved within SLA).
Defect Turnaround – Amber if SLA compliance >= | 60% | ASSUMPTION – not defined in the source KPI workbook; turnaround RAG thresholds (share of defects resolved within SLA).
Defect Rejection – Green if <= | 5% | Source: ATS KPI Data Collation – M.Defects (3.2): Green if rejection <= 5%.
Defect Rejection – Amber if <= | 10% | Source: ATS KPI Data Collation – M.Defects (3.2): Amber if rejection <= 10%, else Red.
Downtime (monthly) – Green if hours <= | 24 | Source: ATS KPI Data Collation – M.Downtime (4.14).
Downtime (monthly) – Amber if hours <= | 48 | Source: ATS KPI Data Collation – M.Downtime (4.14); above this = Red.
Downtime (weekly) – Green if hours <= | 6 | ASSUMPTION – not defined in the source KPI workbook; weekly downtime thresholds (monthly thresholds scaled to a week).
Downtime (weekly) – Amber if hours <= | 12 | ASSUMPTION – not defined in the source KPI workbook; weekly downtime thresholds; above this = Red.
Coverage Target – High Risk | 98% | Source: ATS KPI Data Collation – M.Coverage (3.9).
Coverage Target – Medium Risk | 95% | Source: ATS KPI Data Collation – M.Coverage (3.9).
Coverage Target – Low Risk | 0% | Source: ATS KPI Data Collation – M.Coverage (3.9) (no target for Low risk).
Coverage – Amber tolerance (points) | 2% | Source: M.Coverage (3.9): Amber if within 2 points below target (H >= -2%).
Milestone – Amber window (days before due) | 5 | Source: ATS KPI Data Collation – M.Test Milestone Delays (4.15): Amber if due within 5 days.
Milestone – Amber if share of Amber > | 20% | Source: M.Test Milestone Delays (4.15): overall Amber if more than 20% of milestones are Amber (Red if any Red).
Automation Target | 95% | Source: ATS KPI Data Collation – Q.Automation (4.5): Green if >= 95% or improved vs previous.
CSAT Pass Mark (1-5 score) | 3 | Source: ATS KPI Data Collation – Q.Satisfaction (3.3): pass mark 3.
Resource – Amber if actual >= (share of plan) | 90% | ASSUMPTION – not defined in the source KPI workbook; resource RAG: Green >= 100% of plan, Amber >= this share, else Red.
Execution – Amber if blocked share of planned > | 5% | ASSUMPTION – not defined in the source KPI workbook; the dashboard flags test execution RAG from blocked ÷ planned test cases.
Execution – Red if blocked share of planned > | 20% | ASSUMPTION – not defined in the source KPI workbook; the dashboard flags test execution RAG from blocked ÷ planned test cases.
Commercial – Amber if forecast <= budget + (share) | 5% | ASSUMPTION – not defined in the source KPI workbook; commercial RAG: Green <= budget, Amber <= budget + this share, else Red.
Portfolio Name | <Portfolio Name> | The name this portfolio is shown under in the dashboard's portfolio dropdown and cross-portfolio overview. Must be unique across portfolios.
Programme | HMRC ATS | Groups portfolios under one programme heading.

## Weekly_Snapshot
Weekly_Snapshot
One row per week: environment, coverage, automation, satisfaction, resourcing & commercials and the overall RAG. Coverage / automation / resources / spend are CUMULATIVE to date.
HOW TO FILL: add ONE new row each Friday (new Week Ending). Yellow = type; grey = formula. Leave CSAT blank unless a score was collected that week.
WEEK | ENVIRONMENT |  |  | COVERAGE | [11 empty] | AUTOMATION | [5 empty] | SATISFACTION |  | RESOURCING & COMMERCIALS |  |  |  | OVERALL
Week Ending | Planned Test Days | Downtime Hours | Availability % | High Risk – Requirements | High Risk – Test Cases | High Risk – Covered Reqs | High Risk – Coverage % | Medium Risk – Requirements | Medium Risk – Test Cases | Medium Risk – Covered Reqs | Medium Risk – Coverage % | Low Risk – Requirements | Low Risk – Test Cases | Low Risk – Covered Reqs | Low Risk – Coverage % | Automatable Test Data Setups | Automated Test Data Setups | Test Data Automation % | Automatable Test Cases | Automated Test Cases | Test Case Automation % | CSAT Score (1-5) | CSAT Responses | Resources Planned (FTE) | Resources Actual (FTE) | Cumulative Spend (£) | Forecast at Completion (£) | Overall RAG | Overall Executive Summary | Notes
2026-07-10 | 5 | 2 | 95% | 96 | 80 | 70 | 72.92% | 130 | 100 | 90 | 69.23% | 37 | 30 | 10 | 27.03% | 263 | 10 | 3.802% | 120 | 0 | 0% |  |  | 8 | 8 | 48000 | 800000 | Green | Short narrative for the week: what moved, what is blocked, what you need. | EXAMPLE – delete this row

## Topic_Progress
Topic_Progress
One row per topic per week. All counts are CUMULATIVE to date at that Week Ending.
HOW TO FILL: each Friday add one row for every active topic; pick Topic and Phase from the dropdowns. Executed and % columns calculate themselves.
Week Ending | Topic | Phase | TCs Planned | TCs Designed | Passed | Failed | Blocked | Executed | % Executed | % Designed | Comments | Notes
2026-07-10 | Legacy Penalties – Cycle 1 (Individuals) | SIT | 276 | 200 | 40 | 5 | 8 | 45 | 16.3% | 72.46% | Short comment for the week. | EXAMPLE – delete this row

## Defect_Log
Defect_Log
One row per defect. Aging is in working days (inclusive) from Raised Date to Resolved Date (or today while open).
HOW TO FILL: add each defect when raised; set Resolved Date when fix + confirmation test is complete (or on rejection). Aging and bucket calculate themselves.
Defect ID | Summary | Topic | Test Type | Priority | Severity | Raised Date | Resolved Date | Status | Found In | Owner / DG | TCs Blocked | Triage Comments | Aging (Working Days) | Aging Bucket | Notes
ABC-0001 | Example defect summary | Legacy Penalties – Cycle 1 (Individuals) | SIT | P2 Medium | 4 - Standard | 2026-07-14 |  | Open | Testing | System A | 0 | Triage comments here. | 58 | >10 Days | EXAMPLE – delete this row
Formulas:
Aging (Working Days) = IF(OR([Defect ID]="",[Raised Date]=""),"",MAX(1,NETWORKDAYS([Raised Date],IF([Resolved Date]="",TODAY(),[Resolved Date]),Bank_Holidays!$A6:A60)))

## TSR_Log
TSR_Log
One row per Technical Service Request (TSR) received for impact assessment. Work Days exclude Hold Days.
HOW TO FILL: add the TSR when received; fill Returned Date when sent back to the Front Desk and Hold Days for time pending clarification.
TSR Ref | Description | Topic | Received Date | Returned Date | Hold Days (pending clarification) | Status | Value (£) | Work Days | Over SLA? | Notes
TSR_EXAMPLE-REQ000001 | Example TSR description | Programme (cross-cutting) | 2026-07-06 | 2026-07-14 | 0 | Returned | 10000 | 7 | No | EXAMPLE – delete this row
Formulas:
Work Days = IF(OR([TSR Ref]="",[Received Date]=""),"",MAX(0,NETWORKDAYS([Received Date],IF([Returned Date]="",TODAY(),[Returned Date]),Bank_Holidays!$A6:A60)-N([Hold Days (pending clarification)])))

## Milestones
Milestones
One row per test milestone with due, forecast and completed dates. Delay, status and RAG calculate against today's date.
HOW TO FILL: add each milestone once; set Forecast Date if it slips and Completed Date when done. Critical? = Yes for key milestones.
Milestone | Topic | Due Date | Forecast Date | Completed Date | Owner | Critical? | Delay (Days) | Status | RAG | Notes
Example milestone | Legacy Penalties – Cycle 1 (Individuals) | 2026-12-18 |  |  | Programme Test Manager | No | 0 | On Schedule | Green | EXAMPLE – delete this row
Formulas:
Delay (Days) = IF(OR([Milestone]="",[Due Date]=""),"",IF([Completed Date]<>"",MAX(0,[Completed Date]-[Due Date]),MAX(0,TODAY()-[Due Date])))
Status = IF(OR([Milestone]="",[Due Date]=""),"",IF([Completed Date]<>"",IF([Completed Date]<=[Due Date],"Completed","Completed Late"),IF(TODAY()>[Due Date],"Overdue","On Schedule")))
RAG = IF(OR([Milestone]="",[Due Date]=""),"",IF([Completed Date]<>"",IF([Completed Date]<=[Due Date],"Green","Red"),IF(TODAY()>[Due Date],"Red",IF([Due Date]-TODAY()<=Config!$B30,"Amber","Green"))))

## Readiness
Readiness
SIT readiness per topic per week: overall RAG, six readiness areas (RAG + note) and the road to Green.
HOW TO FILL: each Friday add one row per topic still in preparation; pick RAG from the dropdowns and use short notes (Alt+Enter for new lines).
Week Ending | Topic | Planned SIT Start | Overall RAG | Requirements & Arch Intent RAG | Requirements & Arch Intent – Note | Blockers RAG | Blockers – Note | Resources RAG | Resources – Note | Environments RAG | Environments – Note | Test Scripts & Test Data RAG | Test Scripts & Test Data – Note | Knowledge Transfer RAG | Knowledge Transfer – Note | Road to Green | Notes
2026-07-10 | Sign-Up & Reg – Cycle 1 | 2027-01-11 | Amber | Amber | Arch Intent in review | Green | N/A | Amber | Resourcing uplift under review | Green | IST0 readiness being coordinated | Amber | Script creation in progress | Amber | KT sessions to be scheduled | Close KT session; baseline Arch Intent | EXAMPLE – delete this row

## Commentary
Commentary
Optional narrative per KPI per week (Key Highlights / Area of Concern / Actions Underway / Executive Commentary).
HOW TO FILL: add a row for any KPI you want to explain this week (KPI from dropdown); separate bullets with Alt+Enter. RAG Override only if you disagree with the calculated RAG.
Week Ending | KPI | Key Highlights | Area of Concern | Actions Underway | Executive Commentary | RAG Override | Current Position Override | Notes
2026-07-10 | Overall | Key highlight 1 Key highlight 2 | Area of concern | Actions underway | Executive commentary for the council. |  |  | EXAMPLE – delete this row

## Resourcing
Resourcing
The team roster: role, name, organisation, allocation, dates and status.
HOW TO FILL: add a row when someone joins or is planned; set End Date and Status = Left when they leave. Do not delete history.
Role | Name | Organisation | Allocation % | Start Date | End Date | Status | Notes
Test Analyst (example) | Example Name | Coforge | 100% | 2026-07-01 |  | Active | EXAMPLE – delete this row

## Demand_Forecast
Demand_Forecast
Forward view of Planned vs Available FTE by month (Month = first day of the month).
HOW TO FILL: refresh monthly: one row per future month, Month entered as the 1st of the month.
Month | Planned FTE | Available FTE | Notes
2026-07-01 | 8 | 8 | EXAMPLE – delete this row

## Lessons_Learned
Lessons_Learned
Lessons learned and the improvement action agreed for each.
HOW TO FILL: add a row per lesson; update Status to Actioned when the improvement is in place.
Date | Category | Lesson Learned | Improvement Action | Owner | Status | Notes
2026-07-10 | Process | What we learned. | What we will do about it. | Programme Test Manager | Open | EXAMPLE – delete this row

## Bank_Holidays
Bank_Holidays
England & Wales bank holidays used by the working-day (NETWORKDAYS) calculations. Source: ATS - KPIs - Data Collation.xlsx > Bank Holidays.
HOW TO FILL: extend yearly – add next year's dates below the last row (rows 6–60 are used by the formulas).
Date | Name
2026-01-01 | New Year’s Day
2026-04-03 | Good Friday
2026-04-06 | Easter Monday
2026-05-04 | Early May Bank Holiday
2026-05-25 | Spring Bank Holiday
2026-08-31 | Summer Bank Holiday
2026-12-25 | Christmas Day
2026-12-28 | Boxing Day (substitute for Saturday, 26 December)
2027-01-01 | New Year’s Day
2027-03-26 | Good Friday
2027-03-29 | Easter Monday
2027-05-03 | Early May Bank Holiday
2027-05-31 | Spring Bank Holiday
2027-08-30 | Summer Bank Holiday
2027-12-27 | Christmas Day (substitute for Saturday, 25 December)
2027-12-28 | Boxing Day (substitute for Sunday, 26 December)

## Lists
Priority | Severity | Test Type | Defect Status | Found In | TSR Status | RAG | Yes/No | Phase | Resource Status | Lesson Status | Topic | KPI
P1 High | 1 - Urgent | Smoke | Open | Testing | Open | Green | Yes | Test Prep | Active | Open | Legacy Penalties – Cycle 1 (Individuals) | Overall
P2 Medium | 2 - Very High | SIT | In Progress | Production | Returned | Amber | No | Smoke | Planned | Actioned | Legacy Penalties – Cycle 2 | Risk Based Coverage
P3 Low | 3 - High | E2E | Re-Open |  | Withdrawn | Red |  | SIT | Left |  | Sign-Up & Reg – Cycle 1 | Production Defect Leakage
| 4 - Standard | NFR | Resolved |  |  |  |  | Regression |  |  | Sign-Up & Reg – Cycle 2 | Defect Detection Effectiveness
| 5 - Low | Regression | Closed |  |  |  |  | E2E |  |  | Manage All Unpaid Agents Capacitors | Defect Aging
| 6 - Trivial | Production | Rejected |  |  |  |  | NFR |  |  | Duplicate/Mixed Records & Lockdown Cases | Automation Coverage
|  |  | Deferred |  |  |  |  | TCR / Sign-off |  |  | Manage Designatory Details & Signals | Milestone Delivery
[11 empty] | Manage Designatory Details & Signals – No Repayment Signal | Environment Availability
[11 empty] | SA Digital Data – Enrolment/Registration Support | TSR Impact Assessment
[11 empty] | Notice to File (NTF) | Customer Satisfaction (CSAT)
[11 empty] | Business Income Sources | Resource Position
[11 empty] | Test Automation | Demand Forecast
[11 empty] | Programme (cross-cutting) | Commercial Performance
RAID Health
Test Execution Progress
SIT Readiness
Dropdowns read rows 2–40 of each column. Add new values in the yellow cells below the last item of a list; keep the header text as is.