ATS Dashboard — How to Fill the Data

Step-by-step guide for portfolio teams and the programme lead

Contents

1. The idea in 60 seconds

2. What you get in the box

3. One-time set-up for each portfolio

4. The weekly routine (every Friday, about 5 minutes)

5. Sheet-by-sheet reference

6. POAP — plan on a page

7. RAID log

8. After you fill: load and check

9. How the numbers are worked out

10. Common mistakes

11. Glossary

# 1. The idea in 60 seconds

- One workbook per portfolio. Every portfolio fills the same Excel workbook (ATS_Weekly_Data.xlsx, copied from templates/ATS_Weekly_Data_Template.xlsx).

- Fill it weekly, never overwrite history. Each Friday you add a new dated row (and update any defects, TSRs or milestones that changed). Old rows stay — that is what builds the trends.

- Nothing is entered twice. The Weekly Report, the Monthly Council pack, the Programme Overview and the PowerPoint export are all calculated from the same rows. A month is simply the weeks that end in it.

- Optional extras per portfolio: a POAP workbook (the plan on a page) and a RAID log (your existing RAID file, unchanged).

Look at a finished example first: open samples/ATS_Program_SAMPLE/Self Assessment/ATS_Weekly_Data.xlsx (and its ATS_POAP.xlsx and ATS_RAID_Log.xlsx) next to this guide. All sample data is fictional.

# 2. What you get in the box

| File / folder | What it is | Who uses it |
| --- | --- | --- |
| templates/ATS_Weekly_Data_Template.xlsx | Blank weekly workbook with an example row on every sheet and a built-in Guide sheet. | Every portfolio team |
| templates/ATS_POAP_Template.xlsx | Blank plan-on-a-page workbook (plan bars, milestones, integration flows). | Portfolios that want a roadmap |
| templates/ATS_RAID_Log_Template.xlsx | Blank RAID log with Risks, Issues, Assumptions, Dependencies and Decisions sheets, dropdowns and a user guide. | Portfolios that keep a RAID log |
| samples/ATS_Program_SAMPLE/ | Five fictional portfolios (Self Assessment, PAYE, VAT, Customs Declaration Service, Child Benefit). Self Assessment also has a POAP and a RAID log. | Everyone — to see how a filled workbook looks |
| ATS_Program/ | Your real data folder. Put one subfolder per portfolio here. | Programme lead |
| index.html | The dashboard. Double-click to open (Chrome or Edge). | Everyone |

# 3. One-time set-up for each portfolio

- Create a folder for the portfolio inside ATS_Program/, e.g. ATS_Program/Self Assessment/.

- Copy templates/ATS_Weekly_Data_Template.xlsx into it and rename it ATS_Weekly_Data.xlsx.

- Open the Config sheet. Set Portfolio Name (must be unique across portfolios — it is the name in the dashboard dropdown), Programme, Program Name, Project / Phase, TSR Reference, the managers, Total Budget (£) and the programme dates. Set Data Mode to LIVE.

- Review the thresholds further down Config (SLA days, downtime limits, coverage targets). The defaults are sensible; change them only if your contract says otherwise.

- On the Lists sheet, replace the example Topic values with your portfolio's own topics / releases / workstreams (they feed the dropdowns).

- Delete the grey EXAMPLE rows on each data sheet (the row whose Notes column says "EXAMPLE – delete this row"). Rows marked EXAMPLE are ignored by the dashboard, but delete them anyway.

- Optional: copy templates/ATS_POAP_Template.xlsx as ATS_POAP.xlsx and templates/ATS_RAID_Log_Template.xlsx as ATS_RAID_Log.xlsx into the same folder (or drop in your existing RAID file).

ATS_Program/

├── Self Assessment/

│   ├── ATS_Weekly_Data.xlsx      <- required

│   ├── ATS_POAP.xlsx             <- optional

│   └── ATS_RAID_Log.xlsx         <- optional (your existing RAID format)

├── PAYE/

│   └── ATS_Weekly_Data.xlsx

└── VAT/

└── ATS_Weekly_Data.xlsx

Prefer one flat folder? Name the files ATS_Weekly_Data - <Portfolio Name>.xlsx. A POAP or RAID file is matched to its portfolio when the portfolio name appears in its file name.

# 4. The weekly routine (every Friday, about 5 minutes)

| Sheet | What to do | How many rows |
| --- | --- | --- |
| Weekly_Snapshot | Add ONE new row for this week (Week Ending = the Friday). Enter downtime, coverage, automation, resources, spend and your overall RAG with a one-paragraph summary. | 1 per week |
| Topic_Progress | Add one row per active topic with cumulative test-case counts to date. | 1 per topic per week |
| Defect_Log | Add new defects; update status / Resolved Date of existing ones. Never delete a defect. | as it happens |
| TSR_Log | Add new TSRs when received; fill Returned Date and Hold Days when you respond. | as it happens |
| Milestones | Fill the Completed Date when a milestone is done; adjust the Forecast Date if it moves. | as it happens |
| Readiness | Add one row per topic with six RAG areas and the Road to Green. | 1 per topic per week (optional) |
| Commentary | Optional: your own wording for any KPI. If you leave it empty the dashboard drafts the text for you. | optional |

Monthly / quarterly items (when they change): CSAT score in Weekly_Snapshot, Demand_Forecast, Resourcing, Lessons_Learned.

Then save the workbook. The programme lead opens the dashboard and clicks Refresh data (or Load program folder the first time).

Golden rules: (1) week ending dates must be Fridays; (2) yellow cells are yours, grey cells are formulas — never type over grey; (3) counts in Weekly_Snapshot and Topic_Progress are cumulative to date, not "this week only"; (4) never delete history; (5) keep every portfolio's Portfolio Name unique.

# 5. Sheet-by-sheet reference

Yellow = you type. Grey = calculated. The header text must stay exactly as in the template — the dashboard finds columns by their header.

## 5.1 Config — settings (once)

| Setting | What to enter | Example |
| --- | --- | --- |
| Portfolio Name | The name shown in the dashboard. Unique per portfolio. | Self Assessment |
| Programme | Groups portfolios under one heading. | HMRC ATS |
| Program Name | Full title used in page headers. | HMRC ATS – Self Assessment |
| Project / Phase, TSR Reference | Shown on commercial pages. | Phase 1 / TSR_PR021877-REQ031204 |
| Programme Test Manager, Test Manager | Names for the resourcing page. | role or name |
| Total Budget (£) | Approved budget; the commercial KPI compares the forecast with it. | 760000 |
| Production Go-Live Date | Leave blank until live. While blank, "Production Defect Leakage" shows Not in Production. | (blank) |
| Data Mode | LIVE for real data, SAMPLE for demo data (adds a SAMPLE tag in the dashboard). | LIVE |
| Thresholds | TSR SLA (10 working days), defect SLA (5), rejection %, downtime limits, coverage targets, milestone window, automation target, CSAT pass mark, execution blocked limits. | defaults provided |

## 5.2 Weekly_Snapshot — one row per week

| Column(s) | What to enter | Example (Self Assessment, W/E 2 Oct 2026) |
| --- | --- | --- |
| Week Ending | The Friday of the reporting week. | 2026-10-02 |
| Planned Test Days | Working days testing was planned that week (bank-holiday weeks: 4). | 5 |
| Downtime Hours | Hours test execution was suspended (environment outage etc.). Availability % is calculated. | 0 |
| High / Medium / Low Risk – Requirements | Total requirements tagged at that risk level (cumulative). | 72 / 100 / 48 |
| … – Test Cases | Test cases written against that risk level. | 126 / 189 / 105 |
| … – Covered Reqs | Requirements fully covered by scripts. Coverage % is calculated (covered ÷ requirements). | 72 / 97 / 30 |
| Automatable / Automated Test Data Setups | How many test-data set-ups can be automated, and how many are. | 150 / 108 |
| Automatable / Automated Test Cases | Same for test-case execution automation. | 200 / 150 |
| CSAT Score (1-5), CSAT Responses | Only in a week a score was collected; otherwise leave blank ("Not requested"). | (blank) |
| Resources Planned / Actual (FTE) | Planned vs actual full-time equivalents in place. | 6 / 6 |
| Cumulative Spend (£), Forecast at Completion (£) | Spend to date and the latest forecast. | 608000 / 760000 |
| Overall RAG | Your judgement: Green, Amber or Red. Shown alongside the RAG the dashboard calculates. | Green |
| Overall Executive Summary | One paragraph for the council / report. | "Portfolio remains Green: execution on plan…" |

## 5.3 Topic_Progress — one row per topic per week (cumulative)

| Column | What to enter | Example |
| --- | --- | --- |
| Week Ending, Topic | The Friday and the topic / release / workstream (pick from the dropdown). | 2026-10-02, Self Assessment – Digital Filing |
| Phase | Test Prep, Smoke, SIT, Regression, E2E, NFR or TCR / Sign-off. | SIT |
| TCs Planned / Designed | Test cases planned in scope, and designed (scripted) so far. | 70 / 63 |
| Passed / Failed / Blocked | Cumulative results to date. Executed, % Executed and % Designed are calculated. | 4 / 0 / 0 |
| Comments | Short note. | 4 executed (4 passed, 0 failed); 0 blocked. |

## 5.4 Defect_Log — one row per defect

| Column | What to enter | Example |
| --- | --- | --- |
| Defect ID, Summary | From your defect tool (Jira etc.). | SA-101, Tax calculation – message queued but not delivered |
| Topic, Test Type | Topic dropdown; Smoke, SIT, E2E, NFR, Regression or Production. | Self Assessment – Release 1, Smoke |
| Priority | P1 High, P2 Medium or P3 Low. | P2 Medium |
| Severity | 1 Urgent … 6 Trivial (see the definitions in the Guide). | 3 - High |
| Raised Date | Date raised. | 2026-08-05 |
| Resolved Date | The date work stops (fix and confirmation test done, or the date it was rejected). Blank while open. | 2026-08-06 |
| Status | Open, In Progress, Re-Open, Resolved, Closed, Rejected or Deferred. | Closed |
| Found In | Testing or Production. Production defects drive the leakage KPI. | Testing |
| Owner / DG, TCs Blocked, Triage Comments | Who is fixing it, test cases it blocks, latest note. | Data Team, 0, Fix delivered and confirmed. |
| Aging, Aging Bucket (grey) | Calculated in working days, bank holidays excluded: 0-2, 3-5, 6-10, >10 days. | 2, 0-2 Days |

A Closed or Resolved defect must have a Resolved Date — otherwise its aging cannot be measured (the Data Quality page will flag it).

## 5.5 TSR_Log — one row per Test Scope Request

| Column | What to enter | Example |
| --- | --- | --- |
| TSR Ref, Description, Topic | Reference, short description, topic. | PR022310-REQ032588 |
| Received Date | Date the TSR reached you. | 2026-09-28 |
| Returned Date | Date you sent it back to the front desk with commercials complete. Blank while open (it then ages to today). | (blank) |
| Hold Days (pending clarification) | Working days you were waiting for clarification — these are subtracted. | 0 |
| Status | Open, Returned or Withdrawn (withdrawn TSRs are ignored). | Open |
| Work Days, Over SLA? (grey) | Calculated: working days minus hold days; "Yes" if above the limit in Config (default 10). | 5, No |

## 5.6 Milestones — one row per milestone

| Column | What to enter | Example |
| --- | --- | --- |
| Milestone, Topic, Owner | Name, topic (or Programme), owner role. | Test Completion Report, Programme (cross-cutting) |
| Due Date | The agreed (baseline) date. | 2026-12-18 |
| Forecast Date | Optional: the current forecast if it has moved. | (blank) |
| Completed Date | Fill when done. Completed after the Due Date = late. | (blank) |
| Critical? | Yes for milestones that count towards "critical milestone delay". | No |
| Delay, Status, RAG (grey) | Calculated: Completed / Completed Late / Overdue / On Schedule; Amber in the last 5 days before the due date, Red once overdue. | 0, On Schedule, Green |

## 5.7 Readiness — one row per topic per week (optional)

Columns: Week Ending, Topic, Planned SIT Start, Overall RAG, then for each of six areas — Requirements & Arch Intent, Blockers, Resources, Environments, Test Scripts & Test Data, Knowledge Transfer — a RAG and a Note, and finally Road to Green (what has to happen to turn the topic Green). Example: Overall Green, every area Green, note "Requirements baselined and reviewed."

## 5.8 Commentary — your own words (optional)

One row per KPI per week: Week Ending, KPI (pick from the list), Key Highlights, Area of Concern, Actions Underway, Executive Commentary, optional RAG Override and Current Position Override. Put each bullet on its own line (Alt+Enter). Anything you type here replaces the auto-drafted text for that KPI and is labelled From Excel in the dashboard; blank fields keep the auto draft.

## 5.9 Small tables

| Sheet | Columns | Notes |
| --- | --- | --- |
| Resourcing | Role, Name, Organisation, Allocation %, Start Date, End Date, Status | Status: Active, Planned or Left. Use role names if you prefer not to list people. |
| Demand_Forecast | Month (first day), Planned FTE, Available FTE, Notes | A gap of more than 1 FTE in the next 3 months turns the Demand KPI Red. |
| Lessons_Learned | Date, Category, Lesson Learned, Improvement Action, Owner, Status | Shown on the "Lessons Learned" council page. |
| Bank_Holidays | Date, Name | Used for all working-day maths. Add next year's dates each January. |
| Lists | Dropdown values | Edit Topic here; leave the rest unless you add a new value. |

# 6. POAP — plan on a page

Fill ATS_POAP.xlsx once and update dates and status as the plan moves. The dashboard turns it into a roadmap (Gantt), a one-page poster and an integration-flow explorer.

| Sheet | One row per | Key columns |
| --- | --- | --- |
| POAP_Config | setting | Program Name, Plan Start/End Date, Status Date (blank = today), Data Mode, Pillars and Activity Types with colours |
| POAP_Plan | bar on the roadmap | ID, Pillar, Topic (swim-lane), Activity Type, Item, Start, End, Baseline Start, Baseline End, % Complete, Status, RAG, Owner, Depends On, Scope / Notes |
| POAP_Milestones | milestone | ID, Pillar, Topic, Milestone, Date, Type (SIT Start, SIT End, Sign-off / TCR, Go-Live, Gate…), Status (Planned, Achieved, At Risk, Missed) |
| P2P_Matrix | integration flow | Flow ID, Topic, Sub Process, System Path (System A → System B → System C), Test No, Planned Date, Status, results for 2xx / 3xx / 4xx / 5xx |

### How to fill POAP_Plan

- Start / End are the current plan. Baseline Start / End are the originally agreed dates — fill them once and never change them. The dashboard shows the gap as a ghost bar and a slip badge such as +14d ("Slip (Days)" is calculated).

- Status: Not Started, In Progress, Complete, Delayed, On Hold or Dates TBC. For Dates TBC leave Start and End blank.

- % Complete is 0–100% (type 0.5 or 50%).

- Depends On: the IDs this bar waits for, comma-separated (e.g. A-003, A-004). The roadmap draws the dependency arrows.

- Activity Type decides the bar colour. Use the dropdown: Test Prep, Dependencies, Regression, SIT, Smoke / P2P, Defect Retest, TCR / Sign-off, E2E, NFR, Automation, Holiday / Freeze, Other.

- Rows whose Notes start with EXAMPLE are ignored — delete the example row once you have real rows.

# 7. RAID log

Start a new log from templates/ATS_RAID_Log_Template.xlsx (or keep using your existing RAID file — the dashboard finds columns by their header names). Put it in the portfolio's folder as ATS_RAID_Log.xlsx. It has five log sheets, each with the header on row 10 and data from row 11.

| Sheet | One row per | Key columns |
| --- | --- | --- |
| Risks | risk | Summary Title, Likelihood, Impact (score = L × I → Very Low … Very High), Status (Open / Mitigated / Closed), Mitigation, Owner, Review Date |
| Issues | issue | Summary Title, Priority, Severity, Status (Open / Resolution in progress / Resolved / Closed), Target and Actual Resolution Date |
| Assumptions | assumption | Description, Confidence Level, Validation Action, Validation Due Date, Status (Unconfirmed / Confirmed Correct / Confirmed Incorrect) |
| Dependencies | dependency | Description, Dependency For / From, Type, Date Required, Priority, Status (Open / Closed) |
| Decisions | decision | Summary Title, Decision / Description, Category, Decision Maker / Forum, Date Decided, Rationale, Impact of Decision, Status (Pending / Approved / Rejected / Superseded), Owner, Review Date, Linked Risk / Issue ID |

The dashboard shows open items by rating, a likelihood × impact heat-map, the dependencies due in the next 30 days and the Decisions table (pending first, then the most recent). Decisions marked Pending count as open and appear under "Actions Underway"; decisions whose Date Decided falls in the month or week are counted in the highlights. An old RAID file without a Decisions sheet is fine — that part simply shows "No decisions logged". RAID Health is Red when a Very High item is open and Amber when a High item is open. A closed risk or a resolved issue drops out automatically; set Archived = Yes to hide any row.

# 8. After you fill: load and check

- Open index.html. Click Load program folder and choose ATS_Program (first time), or Refresh data after later edits.

- Use the Portfolio dropdown (top bar) to switch between portfolios, or Programme Overview to see them all.

- Open Appendix → Data Quality in the Monthly Council or Weekly Report. It lists problems such as a closed defect without a Resolved Date, a TSR returned before it was received, or a week ending that is not a Friday.

- Use Export PowerPoint for slides (built on the client PowerPoint theme; charts and tables stay editable), Export PDF for a document you can read or print (the Monthly Council and Weekly Report export every page of the pack), or Copy as picture on any single page.

# 9. How the numbers are worked out

| KPI | Rule (thresholds are editable in Config) |
| --- | --- |
| Risk Based Coverage | Covered ÷ requirements per risk level. Green at or above target; Amber within 2 points; else Red. Overall = worst of High and Medium. |
| Production Defect Leakage (quarterly) | Red if any P1, or 5+ P2, or 6+ P3 found in production in the quarter; Amber for any P2/P3; else Green. |
| Defect Detection Effectiveness | Defects found in testing ÷ (testing + production). Rejection rate Green ≤ 5%, Amber ≤ 10%. |
| Defect Aging | Working-day buckets; Green if at least 80% resolved within 5 working days, Amber at least 60%, else Red. |
| Automation Coverage (quarterly) | Green if at or above target, or improving on the previous period. |
| Milestone Delivery | Red if any milestone is overdue or late; Amber if more than 20% are Amber. |
| Environment Availability | 1 − downtime ÷ (test days × 8). Monthly: Green ≤ 24h, Amber ≤ 48h. Weekly limits are in Config. |
| TSR Impact Assessment | Red if any TSR takes more than 10 working days (hold days excluded). Open TSRs age to today. |
| Customer Satisfaction (quarterly) | Pass mark 3 of 5; Green if at or above it and not declining. |
| Resource / Demand / Commercial | Actual ÷ planned FTE; FTE gap in the next 3 months; forecast vs budget (Amber within 5% over). |
| RAID Health | Red with a Very High item open; Amber with a High item open. |
| Test Execution Progress | Blocked ÷ planned: Green ≤ 5%, Amber ≤ 20%, else Red. |

### How weekly rows become a month

- Added up: planned test days and downtime hours.

- Latest week in the period: coverage, automation, test execution, resources, spend, forecast.

- Filtered by date: defects, TSRs, milestones.

- A week belongs to the month it ends in. Every month is calculated as of its last day, so last month's pack never changes when you add new rows.

# 10. Common mistakes

| Mistake | What happens | Fix |
| --- | --- | --- |
| Week Ending is not a Friday | Flagged on the Data Quality page; the week may land in the wrong month. | Use the Friday of that week. |
| Typed "this week only" numbers in Weekly_Snapshot / Topic_Progress | Coverage and execution fall instead of grow. | Enter cumulative totals to date. |
| Deleted old defect/TSR rows | Past months change and trends break. | Keep history; change Status instead. |
| Closed a defect without a Resolved Date | Aging cannot be measured. | Add the date work stopped. |
| Two workbooks with the same Portfolio Name | One portfolio disappears from the dropdown. | Make the names unique. |
| Typed over a grey formula cell | Calculated column stops updating. | Restore the formula from the template. |
| Left the EXAMPLE row in | Ignored by the dashboard, but confusing. | Delete it. |
| Forgot to click Refresh data | The dashboard still shows the previous load. | Click Refresh data. |

# 11. Glossary

| Term | Meaning |
| --- | --- |
| RAG | Red / Amber / Green status. |
| TSR | Test Scope Request — a request to estimate or scope testing, answered within an SLA. |
| SLA | The agreed response time (default 10 working days for a TSR, 5 for defect turnaround). |
| SIT / E2E / NFR | System Integration Test, End-to-End test, Non-Functional test. |
| P2P | Point-to-point integration test between two systems. |
| POAP | Plan on a Page — the programme roadmap. |
| RAID | Risks, Assumptions, Issues, Dependencies. |
| FTE | Full-time equivalent. |